SUMMARY OF CONCLUSIONS

Technical meeting MA-NA-JS - programming experts on Programming process

via Zoom, October 30th, 2020

Participants:

Managing Authority: Mrs. Diana Gheorghe

National Authority: Mrs. Horváth Nikoletta, Ms. Hujbert Szilvia, Mr. Molnár Tamás, Mr. András Stefanik

Joint Secretariat: Mrs. Monica Terean, Mrs. Adriana Ghiță, Mrs. Cristina Vesa, Mr. Marius Olariu

Urbasofia: Mrs. Gloria Zagaglioni- programming expert

The following subjects were discussed at the meeting:

- Follow-up of the consultation workshops organised between 19-23.10.2020

- Steps to be further made in relation to programming process

- AOB

Objective of the meeting:

The technical meeting was organized in the context of programming process, in order to discuss the status of programming process, main conclusions of the consultations workshops and next steps to be further undertaken

- Follow-up of the consultation workshops organised between 19-23.10.2020

The main participants in the events were stakeholders in the Programme area – local and regional level, as well as representatives of relevant central institutions in both Member States.

It has been underlined that the purpose of the 6 on-line consultation workshops organised between 19-23.10.2020 was to gather qualitative information from local/regional/central level to be integrated in the Territorial Analysis (TA), so that the Consortium experts’ desk-based work could be complemented by and enriched with inputs coming from the “field”. Also, the importance of getting information on missing/incomplete data, that might be available only to local/regional stakeholders, was also emphasized.

The relevant aspects raised during the meetings, the feed-back to be received from the participants when answering the short questionnaire sent to them after the events, the relevant documents and statistics to be submitted by them following Programme’s request, are going to be analysed and processed so that the Consortium experts could finalize the Territorial Analysis.

B. Steps to be further made in relation to programming process

A first “readable” version of the Territorial Analysis, integrating relevant data obtained following the 19-23.10 events, will be submitted to the MA/NA by November 9th and to the Programming Committee (PC) members by November 13th. In parallel, possible scenarios on Policy Objectives (PO) selection will be drafted and analysed by MA and NA, in order to be presented and approved, together with the TA, within the second PC meeting to be organized at the end of November.

The proposed scenarios will present the best options in relation to PO/ISOs: what POs/ISOs are recommended to be financed under the future programme, what should not be selected, as well as identified alternative solutions (e.g.: to finance operations related to border management under PO4/ISO1 instead of ISO2). So far, based previous discussions and taking also into account the latest version of Interreg Regulation, the most probable scenario could be: PO2 and PO4 (being mandatory) and ISO1 (being the agreed option from several points of view).

The intervention logic could be presented and approved either within the second PC Meeting, or developed afterwards, following the selection of the POs/ISOs.

C. AOB

Technical meetings between Programme’s structures are envisaged during November for aspects concerning TA, TIA, scenarios, intervention logics etc.