| 1st Open Call – People to People Projects |  |
| --- | --- |
| Project code & acronym | ROHU00224 – InnoCoop |
| Project title | Innovative Cooperation for a better cooperation governance in cross-border area |
| Priority | P3 - A more sustainable, community-based and effective cross-border cooperation |
| Specific Objective | ISO6.3 - Building up mutual trust, in particular by encouraging people-to-people actions |
| Implementation period | 12 months (July 28th 2025 – July 27th 2026) |
| Objective | The overall objective of the project is to have a more sustainable and effective cross-border cooperation between institutions, with the aim of the proposed training to familiarise participants with innovation management as a tool for development and its practical implementation. |
| Partnership | Lead Partner: Asociația de Dezvoltare Intercomunitară Zona Metropolitană Oradea (Romania) |
|  | Project Partners: PP2 HU: DKMT Duna-Körös-Maros-Tisza Eurorégiós Fejlesztési Ügynökség Nonprofit Közhasznú Kft. (Hungary) PP3 HU: Hajdú-Bihar Vármegyei Fejlesztési Ügynökség Nonprofit Kft. (Hungary) PP4 RO: Asociația de Dezvoltare Intercomunitară Transregio (Romania). |
| Total budget | EUR 237,568.80, out of which ERDF EUR 190,055.04 |
| Summary | The project’s objective will be reached through the implementation of the following activities: - Organising Innovation Management trainings in RO for the representatives of 12 local authorities from the Oradea Metropolitan Area and other representatives from public institutions and NGOs (2 groups, 3 days of training, with a participation diploma for 30 people). - Organising the training in Innovation Management in HU (12 participants from RO, 12 from HU and 2 trainers). - Elaborating a Joint strategy based on the experience of the training and interviews - how to continue to spread innovation in the border region. - Exchange of experience visit in Oradea with representatives from institutions from Hajdú-Bihar and Csongrád-Csanád Counties, Bihor County and representatives from other stakeholders and interested groups, including citizens. - Joint workshop on efficiency of public funds in Hu, for people working in public administration (12 participants from RO and 12 from Hu). - Workshop on Cross-border transport in economic development of the RO-HU area; one-day event with an estimated 12 participants from HU and 20 from RO - Classes on financial management in schools, to promote financial literacy – at least 12 different schools in Hungary and 10 in Romania, thus reaching an estimated number of 600 students. - Contributing to increased training effectiveness, ensuring that participants have the necessary tools to acquire and apply knowledge effectively, by endowing the PPs with office devices/mobility equipment. |
| Main results | In summary, this project is innovative, comprehensive, and promotes cross-border collaboration, making it a valuable initiative for improving the capacity of local administrations and ultimately benefiting citizens in the region by building mutual trust through people-to-people actions from the project. The project aims to achieve several key results: - The common capacity building achieved by attending Innovation Management trainings (people-to-people actions). - Participants from the local administrations in neighbouring regions benefit from exchange solutions and experiences through collaborative efforts. - More effective service delivery for the local administrations through cross-border cooperation, enabled by the transfer of knowledge and best practices from one region to another. - One strategic cross-border document elaborated and taken up by partners (and also disseminated to other institutions as a best practice example). - Contributing to long-term stability and development through a cross-border approach, strengthening regional cooperation and fostering goodwill between neighbouring areas. - Students of different ages equipped with practical life skills that will serve them well in adulthood, enhancing their ability to navigate the complexities of the modern financial world. |