| 2nd Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-161 |
| Project title | O-IKT-SETI O-IKT (Sport-Health-Tourism-Youth) |
| Priority axis | 6 – Promoting cross-border cooperation between institutions and citizens (Cooperation of institutions and communities) |
| Investment priority | 11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions (Cooperation for citizens) |
| Implementation period | 25 months (1st of December 2018 – 31st of December 2020) |
| Objective | The project’s main objective was to draw attention to a healthy, responsible, environmentally conscious lifestyle through orienteering sports. |
| Partnership | Lead Beneficiary: Regional Telecottages Public Association of South Hungarian Plain (Hungary) |
|  | Project partners: PP2: For Orienteering Foundation (Hungary) PP3: The Touristic Association Condor Club Arad (Romania) |
| TOTAL Budget | € 64,939.00, out of which ERDF € 55,198.15 Total eligible expenditure certified within the project: € 54,315.94 Budget execution: 83.64% |
| Summary | The project ROHU-161 aimed to intensify cooperation between cross-border communities, from Arad and Csongrád-Csanád counties, and promote a healthy lifestyle through sport. The main activities implemented within the project: - Organising activities to collect data (800 digitally recorded research documents such as interviews, pictures, and films), systematising and preparing them for selection and promotion on the portal; - Organising a seminar to select the areas where the events will be held and to select the values that will be promoted (40 values selected from 8 areas (5 RO+3 HU)); - Organising a 4-module online training/webinar to educate and inform the target group about the newly developed orienteering areas and to involve rural regions in digital development; - Developing a portal to promote the 8 selected areas and sports tourism in the border area; - Organising an orienteering map correction training for 14 people (7 from RO and 7 from HU); - Organising the map correction for 5 Romanian and 3 Hungarian regions selected, with teachers acting as proofreaders and mentors. 13 maps were produced in the 8 locations, with the involvement of students participating in the workshops. As a result, 38.58 square km of mapped areas were corrected; - Organising promotional orienteering events in 5 Romanian and 3 Hungarian settlements from the Programme area using the created maps and purchased devices, with 208 participants; - Purchasing equipment for carrying on the activities (such as 6 notebooks, 1 monitor, 2 mobile phones, 6 SD cards, 1 GPS, 1 Forestry laser rangefinder, 1 Kramer software, etc). On December 31, 2020, the project was successfully finalised. All activities provided in the project were completed (100%). The Programme Output Indicator was „11/b2 Number of people directly involved in cross-border cooperation initiatives”. A total of 330 people from Romania and Hungary, directly involved in cross-border cooperation initiatives, participated in the ROHU–161 project activities. The project drew attention to healthy lifestyles and the importance of outdoor activities and sports as key factors in improving quality of life for all age groups. |
| Main results | The main results of the project are: - 330 people from Romania and Hungary participated in the project’s activities; - 1 bilingual portal developed to promote the natural and cultural values, the orienteering sports events, and the virtual routes from the 8 cross-border areas selected; - 8 map corrections for 5 selected Romanian areas (Căsoaia, Moneasa, Băile Felix, Sânnicolau de Munte, and Vârtop) and 3 Hungarian areas (Ásotthalom, Sándorfalva and Ópusztaszer Memorial Park) - 38,58 square km of mapped areas; - 8 orienteering sports tourism centres were established in the Programme areas (5 in Romania and 3 in Hungary - Căsoaia, Moneasa, Băile Felix, Sânnicolau de Munte, Vârtop, Sándorfalva, Ópusztaszer and Ásotthalom) through the 8 orienteering sports events organised for 208 participants; - 1 orienteering map correction training organised for 14 participants; - 4 online module training/webinars were organised for 60 participants. Website/webpage: https://o-sportturizmus.ertekek.hu/ Social media: Facebook O-IKT-SETI |