| 3rd Open Call for Proposals 3rd Open Call for Proposals |  |
| --- | --- |
| Project code | ROHU-401 |
| Project title | HEARTS&LIVES Improving health-care standards in prevention, identification and treatment of cardiovascular and gynaecological diseases in crossborder area |
| Priority axis | 4 – Improving health-care services (Cooperating on health-care and prevention) |
| Investment priority | 9/a - Investment in health and social infrastructure which contributes to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services. |
| Implementation period | 29 months (March 1, 2019 – July 31, 2021) |
| Objective | The main objective was to improve cardiovascular and gynecological healthcare services, both preventive and curative, across Timiș, Bihor, and Hajdú-Bihar counties. |
| Partnership | Lead Beneficiary: Institute of Cardiovascular Diseases Timișoara (Romania) |
|  | Project Partners: PP2: County Clinical Emergency Hospital in Oradea (Romania) PP3: University of Debrecen (Hungary) |
| TOTAL Budget | € 3,000,000.00 out of which ERDF € 2,550,000.00 Total eligible expenditure certified within the project: € 2,936,411.47 Budget execution: 97.88% |
| Summary | Project ROHU-401 aimed to improve the healthcare services across the three counties by purchasing and installing modern medical equipment and also by preventing and diagnosing diseases with high frequency in the eligible area, with special attention to disadvantaged groups. The main activities implemented within the project: - Acquisition and equipping of 3 healthcare departments (Cardiovascular Surgery, Cardiology, and Sterilization) within the Institute of Cardiovascular Diseases Timișoara; - Acquisition and equipping of 2 healthcare departments (Gynecological Surgery and Intensive Care) within the County Emergency Clinical Hospital in Oradea; - Acquisition and equipping of 2 healthcare departments (Obstetrics–Gynecology, and Cardiology and cardiac surgery) within the University of Debrecen; - Organizing campaigns for health screening and prevention activities for 700 patients, to prevent and diagnose high-frequency diseases in the eligible area; - Organizing a campaign consisting of free consultations offered to more than 200 persons with low incomes and from disadvantaged groups, to improve their access to health infrastructure; - Organizing Know-how exchange and capacity-building activities (online training courses and workshops) between project partners for 80 physicians and medical assistants. On July 31, 2021, the project was successfully finalized. All activities provided in the project were completed (100%). The Programme Output Indicators are „9/a 1 Population having access to improved health services” and „9/a 2 Number of healthcare departments affected by modernized equipment”. Through project ROHU–401, 1,600,391 people (759,819 population of Timiș County, 314,408 female population of Bihor County, and 526,164 population of Hajdu-Bihar County) benefited from improved healthcare services, and 7 healthcare departments are more efficient using modernized equipment purchased through the project. |
| Main results | The main results of the project are: - 1,600,391 people benefited from improved healthcare services, and 7 healthcare departments are more efficient using modernized equipment purchased through the project for the Institute of Cardiovascular Diseases Timișoara, Oradea County Emergency Clinical Hospital, and the University of Debrecen; - health screening promoted and provided information for the prevention and diagnosis of high-frequency diseases in the eligible area; - 255 persons from disadvantaged groups had improved access to health infrastructure (LB - 155 persons, PP2 - 100 persons); - the institutional capacity of the partners improved through know-how exchange and capacity-building activities (training courses and conferences) between project partners, as follows: 40 physicians and medical assistants of PP2 participated in the 5 workshops and trainings organized by PP3 and 56 persons of LB's medical staff participated to the online workshop and live-case demonstration organized by PP3. Social media: https://www.facebook.com/rohu401 Website/webpage: - http://www.cardiologie.ro/data_files/proiect-rohu/PROIECT-ROHU-401.html - https://rohu401.spitaljudetean-oradea.ro/ - https://palyazatok.unideb.hu/az-egeszsegugyi-ellatas-szinvonalanak-fejlesztese-kardiovaszkularis-es-nogyogyaszati-megbetegedesek |