| 1st Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-41 |
| Project title | SafeArea Safer communities in the cross-border area by improved disaster management |
| Priority axis | 5 – Improve risk-prevention and disaster management (Cooperation on risk-prevention and disaster management) |
| Investment priority | 5/b – Promoting investment to address specific risks, ensuring disaster resilience and developing disaster management systems. |
| Implementation period | 21 Months (April 1, 2018 - December 31, 2019) |
| Objective | The project's main objective was to improve fire risk management and rescue operations for the following 11 localities in the border area: Valcani, Dudeștii Vechi, and Sânnicolau Mare from Romania, and Földeák, Óföldeák, Pitvaros, Királyhegyes, Kiszombor, Apátfalva, Magyarcsanád and Csanádpalota from Hungary. |
| Partners | Lead Beneficiary: Valcani Commune (Romania) |
|  | Project partner: Municipality of Földeák (Hungary) |
| TOTAL Budget | € 434,151.60 out of which ERDF € 369,028.86 Total eligible expenditure certified within the project: € 421,873.44 Budget execution: 97.17% |
| Summary | The project aimed to have well-trained volunteer firefighters, with access to professional tools and equipment, crucially needed in case of disasters, using not only the equipment but also the priceless know-how regarding behavior, action plan, and best procedures in case of risks. The main activities implemented within the project: - Organizing 6 awareness-raising campaigns for at least 150 pupils – LB; - Organizing 3 awareness-raising campaigns for 90 parents – LB; - Organizing 3 public safety days in Valcani, Sânnicolau Mare, and Dudeștii Vechi - LB; - Organizing 12 awareness-raising campaigns for at least 300 pupils – PP; - Organizing 8 awareness-raising campaigns for 240 parents – PP; - Organizing 3 public safety days in 3 different localities from Csongrád-Csanád County - PP; - Organizing 12 training sessions for 30 volunteer firefighters - LB; - Elaboration of 1 Joint protocol of interventions; - Purchasing special vehicles and equipment for emergency response (1 fire engine and 6 protection equipment) - LB; - Organizing 6 training sessions for 33 local volunteers - PP; - Organizing 3 joint practical exercises for 63 volunteers (33 from Földeák, 30 from Valcani) - PP; - Purchasing equipment for emergency response (1 fire engine and 7 pumps) - PP; - Organizing meetings with members of local communities to train them regarding prevention methods, first aid techniques, etc. On December 31, 2019, the project was successfully finalized. All activities provided in the project were completed (100%). The Project Output Indicator was 5/b 1 Population safeguarded by improved emergency response services. Through the project ROHU-41, 36,749 people are better safeguarded by improved emergency response services. |
| Main results | The main results of the project are: - 2 teams of volunteer firefighters from Valcani and Földeák are better equipped (2 fire trucks, 7 pumps, and 6 sets of protection equipment) and prepared (18 training sessions for volunteer firefighters and 3 joint exercise sessions) to act in 11 localities from the border area; - 29 awareness campaigns and 6 public safety days to raise awareness on risk prevention for the population of Timiș and Csongrád-Csanád Counties; - 1 joint intervention protocol for the project partners. Joint Protocol: https://interreg-rohu.eu/wp-content/uploads/2020/03/ROHU41_-Joint-Protocol.pdf Website/web page: www.safearea.ro |