| 3rd Open Call for Proposals |  |
| --- | --- |
| Project code | ROHU-382 |
| Project title | YES Youth Entrepreneurship Support |
| Priority axis | 3 – Improve employment and promote cross-border labour mobility (Cooperating on employment) |
| Investment priority | 8/b - Supporting employment-friendly growth through the development of endogenous potential as part of a territorial strategy for specific areas, including the conversion of declining industrial regions and enhancement of accessibility to, and development of, specific natural and cultural resources |
| Implementation period | 22 months (1st of March 2019 – 31st of December 2020) |
| Objective | The project's main objective was to increase the employment rate of young people in the Romanian-Hungarian border area by providing them with entrepreneurial skills and a professional (online) framework, as they already have the necessary skills for self-employment, entrepreneurship and business creation. |
| Partnership | Lead Beneficiary: Association of Business Promotion in Romania (Romania) |
|  | Project Partners: PP2: Revita Foundation (Hungary) |
| TOTAL Budget | € 293,504.50 out of which ERDF € 249,478.82 Total eligible expenditure certified within the project: € 210,542.05 Budget execution: 71.73% |
| Summary | The project ROHU-382 aimed to raise the employment rate in the Romanian-Hungarian border area by supporting self-employment. The main activities implemented within the project: - Development of joint training methodology with 1 Online competency test with creative tasks for the students, giving an automatic response for every person; 1 E-learning platform; 1 E- curriculum; 1 Bootcamp script and 1 practical guide to entrepreneurship training; - Joint delivery (joint entrepreneurship training) which contained: 100 Online competency assessments for 100 students, 3 boot camps, meaning online simulation-based intensive training camps for 100 students (1 in RO and 2 in HU); - 1 cross-border strategy which included a baseline report about the four counties of the project area and an Integrated development strategy - 1 Caravan was organized by LB, with an expert speaker on entrepreneurship – visiting 6 cities in the four counties (and more than 8 high schools) - 2-day Cross-border teacher workshop organised for 15 teachers in Romania so they could learn about the current and most effective tools and methods of entrepreneurship education; On December 31, 2020, the project was successfully finalised. All activities provided in the project were completed (100%). |
| Main outcomes | The main deliverables: - 1 cross-border strategy which includes a baseline report about the four counties of the project area and an Integrated development strategy; - Development of joint training methodology with : 1 Online competency test with creative tasks for the students, giving an automatic response for every person; ; 1 E-learning platform; 1 E-curriculum; 1 Bootcamp script and 1 practical guide to entrepreneurship training; - 5 Project videos, 1 Website to promote the projects activities and last but not least 3 social media accounts were created (Facebook, Instagram, Youtube) through which will be disseminate only information directly concerning the project. - To involve teachers and schools, 1 Caravan was organized by LB, with an expert speakers on entrepreneurship – visiting 6 cities in the four counties (and more than 8 high schools); - 2-day Cross-border teacher workshop was organized for 15 teachers in Romania so they could learn about the current and most effective tools and methods of entrepreneurship education; - Joint delivery (joint entrepreneurship training) which containes : 100 Online competency assessments for 100 students, 3 bootcamps meaning online simulation-based intensive training camps ( 1 in RO and 2 in HU). The main results achieved: The project raised the employment rate in the Romanian-Hungarian border area by supporting self-employment. At the end of this project, 100 young students learned how to develop a creative business and become a strategic entrepreneurs. The main indicator: The Programme Output Indicator was „CO44 Labour Market and Training: Number of participants in joint local employment initiatives and joint training”. Through the ROHU-382 project, 100 young students involved in joint entrepreneurship training with highly developed entrepreneurial competencies and further learning potential were able to successfully enter the labour market. Website/webpage: https://yesbiz.eu/ro/ Social media: https://www.facebook.com/YESyouthentrepreneurshipsupport |