| 1st Open Call- Normal Project Proposal |  |
| --- | --- |
| Project code | ROHU-29 |
| Project title | AQUARES Conservation and protection of ecosystems endangered by lack of thermal and freshwater in crossborder area |
| Priority axis | 1 – Joint protection and efficient use of common values and resources (Cooperating on common values and resources) |
| Investment priority | 6/c- Conserving, protecting, promoting and developing natural and cultural heritage |
| Implementation period | 34 months (1st of May 2018 – 28th of February 2021) |
| Objective | The project's primary objective was to preserve and protect ecosystems endangered by the scarcity of thermal water and freshwater in cross-border areas. |
| Partnership | Lead Beneficiary: Oradea Metropolitan Area Intercommunity Development Association (Romania) |
|  | Project Partners: PP2: Aqua Crisius Angling Association (Romania) PP3: University of Oradea (Romania) PP4: Institute for Nuclear Research (Hungary) |
| TOTAL Budget | € 1,346,941.55 out of which ERDF € 1,144,900.31 Total eligible expenditure certified within the project: € 1,259,099.31 Budget execution: 93,48% |
| Summary | The project aimed to find solutions to increase the protection of the underground thermal waters and to improve the thermal species conservation status in Bihor and Hajdú-Bihar counties. The project activities investigated the natural hydrogeological conditions as a result of over-exploitation and determined the drying up of the thermal springs/water from the natural reservations "Băile 1 Mai (Bihor county, RO)" and "Pocsaji-kapu (Hajdú-Bihar county, HU)", to establish the conditions and criteria necessary for the revitalization of the underground thermal waters. The main activities implemented within the project: - Creating the Metropolitan Center for Geothermal Development, located in Oradea, equipped with furniture, laboratory and IT equipment, used to encourage and support initiatives regarding the protection and proper use of geothermal resources -LB - Renovation of the pool of the University of Oradea campus and using it for the relocation of the water lily species Nymphaea Lotus Thermalis -PP3 - Organizing the Open Day event to visit the protected area of the Băile 1 Mai Nature Reserve, an event attended by over 200 people, both children and adults -PP2 - Elaborating a study on the possibility of developing ecotourism in the area by creating cycling routes, thematic routes, as well as a dedicated marketing plan - Hiring a ranger and purchasing a patrol vehicle to ensure the monitoring of the protected natural area-PP2 - Purchasing the biology and chemistry laboratory equipment for carrying out research activities related to the water lily species Nymphaea Lotus thermalis variant -PP3 - Elaborating a theoretical study on the species Nymphaea Lotus Thermalis based on research and laboratory analyses carried out by PP3 - Promoting the protected area in Băile 1 Mai (RO) and water lily species by editing 500 albums and making 2 films - LB - Organizing a campaign to clean Petea and Hidișel streams (RO), part of an action called No Litter Strategy, to improve the habitat conservation status for flora and fauna species in the area - PP2 - Researching and revitalizing the Tövises-meder aquatic habitat in the "Pocsaji-kapu" nature reservation, Hungary, by developing a paleobotanical study based on the research activities carried out in the Natura 2000 research site - Elaborating six studies on the possibility of restoring the thermal springs developed as a result of the research activities, the analyses and the studies carried out on the springs that need revitalizing in the Băile 1 Mai area. On February 28, 2021, the project was successfully finalized. All activities provided in the project were completed (100%). |
| Main outcomes | The main deliverables: 1) The Metropolitan Center for Geothermal Development rehabilitated; 2) 1 Protected Area clean-up campaign- 30 participants organized a hygiene campaign in the Petea and Hidisel streams, the Petea brook, in the meadow and in the fenced area; 3) 1 Eco-tourism concept study finalized; 4) 1 Bacteriological study elaborated; 5) 1 Paleobotanical study elaborated; 6) 6 Studies on restoration of thermal springs elaborated; 7) 1 Renovated pool with thermal water lilies, where the protected species of thermal lilly will be relocated from the greenhouse. This pool mimics the natural conditions, a permanent course of geothermal water was provided. The main results of the project were: - Better conservation status of thermal species in Protected Areas in Romania and Hungary (372 ha in Petea Natural Park and 284 ha in „Pocsaj-kapu” Protected Area), especially of the thermal lily or dretea (Nymphaea lotus var. thermalis), the snail (Melanopsis parreyssii) and the Thermal Rudd (Scardinius racovitzai). - A renovated pool assuring better conservation conditions for the thermal lilies in Oradea University Camp. - 9 studies completed, helping the characterization and research of hydrogeological conditions necessary for restoration and operation of thermal springs, thus providing a better conservation status for thermal species in Romania and Hungary. The main indicator: The Programme Output Indicator is „CO23 Nature and biodiversity: Surface area of habitats supported to attain a better conservation status”. Through the project ROHU-9, 656 ha of land has attained better conservation status. Website/webpage: https://aquares.ro/ https://zmo.ro/download/Rezumat%20proiect%20ROHU29%20RO.pdf |