| 3rd Open Call for Proposals |  |
| --- | --- |
| Project code | ROHU-374 |
| Project title | TwinS Cross-border joint training centres |
| Priority axis | 3 – Improve employment and promote cross-border labour mobility (Cooperating on employment) |
| Investment priority | 8/b - Supporting employment-friendly growth through the development of endogenous potential as part of a territorial strategy for specific areas, including the conversion of declining industrial regions and enhancement of accessibility to, and development of, specific natural and cultural resources |
| Implementation period | 46 months (March 01, 2019 – December 31, 2022) |
| Objective | The project's main objective was to increase the labour force mobility and employment opportunities in the cross-border area through two training modules organised: Orientation and cross-border career planning (HU)/ Training in civic and social skills (RO), and Basic Entrepreneurial Knowledge (in both countries). |
| Partnership | Lead Beneficiary: “Bartók Béla” Theoretical High School (Romania) |
|  | Project Partners: PP2: Catholic House Public Benefit Non-profit Ltd (Hungary) PP3: Diaspora Foundation (Romania) |
| TOTAL Budget | € 1,269,162.83 out of which ERDF € 1,078,788.40 Total eligible expenditure certified within the project: € 1,250,016.63 Budget execution: 98.49% |
| Summary | The ROHU-374 project aimed to increase the transnational mobility of the labour force through training materials and training modules. Also, it aimed to improve cross-border access to the labour market and increase employment opportunities for people from both sides of the border. The main activities implemented within the project: - Elaboration of 2 training materials in Hungarian and Romanian languages for Career orientation (suited for a 30-hour-long training) and for Entrepreneurial training (suited for a 40-hour-long training); - Organisation of Social and civic competencies training in Romania for 153 unique persons (10 groups) and Entrepreneurial basic knowledge training for 79 unique persons (4 groups); - Organisation of Cross-border career orientation and planning training in Hungary for 126 unique persons (8 groups) and Entrepreneurial basic knowledge training for 80 unique persons (4 groups); - Construction/rehabilitation of a 3-floor training Centre in Zolt, Romania, and endowment of the centre with furniture and equipment; - Construction of a 2-floor training Centre in Domaszek, Hungary, and endowment of the centre with furniture and equipment; - Elaboration of a webpage: http://twinstraining.eu/. On December 31, 2022, the project was successfully finalised. All activities provided in the project were completed. |
| Main outcomes | Deliverables: - 2 centres created for training, specialisation, and support in Zold, Romania, and Domaszek, Hungary; more than 438 people trained in the cross-border area; - 2 training materials elaborated in the Hungarian and Romanian languages for Career orientation and Entrepreneurial training. Results: - increased employment opportunities and enhanced the inclusive growth of the border area through the training modules: Cross-border Career orientation and planning, Social and civic competencies, and Entrepreneurial basic knowledge; - improved the cross-border access to the labor market for more than 430 persons participating in the training sessions: more than 230 Romanian and more than 200 Hungarian participants obtained diplomas. Indicators: The Programme Output Indicator is „CO44 Labour Market and Training: Number of participants in joint local employment initiatives and joint training”. Through project ROHU–374, 438 persons benefited from trainings/ specializations / joint local employment initiatives. Website: www.twinstraining.eu |