| 3rd Open Call for Proposals |  |
| --- | --- |
| Project code | ROHU-386 |
| Project title | CBC-HOSPEQUIP Improving cross-border health care services with modernized medical equipment within Dr. Gavril Curteanu Hospital in Oradea and Békés County Central Hospital |
| Priority axis | 4 – Improving health-care services (Cooperating on health-care and prevention) |
| Investment priority | 9/a - Investment in health and social infrastructure which contributes to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services. |
| Implementation period | 24 months (November 01, 2019 – October 31, 2021) |
| Objective | The main objective was to promote a sustainable health service on both sides of the border with the help of the latest generation of medical devices and by setting up joint protocols in terms of prevention, diagnosis and treatment through the telemedicine system. |
| Partnership | Lead Beneficiary: Municipal Hospital Dr. Gavril Curteanu Oradea (Romania) |
|  | Project Partners: PP2: Békés County Central Hospital (Hungary) |
| TOTAL Budget | € 2,954,338.00 out of which ERDF € 2,511,187.30 Total eligible expenditure certified within the project: € 2,878,493.21 Budget execution: 97.43% |
| Summary | The project ROHU-386 aimed to establish an interconnected health service system between Oradea and Békés County hospitals and increase the quality of services, reducing hospitalization time, and reducing time for accurate/appropriate diagnosis and treatment, therefore creating a major positive impact at the level of Oradea and Békés county. The main activities implemented within the project: - Acquisition and installation of 2 Telemedicine systems (hardware and software components), one for each partner, that will be interconnected; - Purchasing 20 pieces of medical equipment: 1 Magnetic resonance imaging (MRI), 3 ultrasounds, 1 Digital Radiography-scope device mobile, 5 High Performance Mechanical Ventilation Device, 1 Digital Radiography - scope device, 1 Vacuum Transport System for Laboratory and Medicinal Samples, 1 Full 3D Full HD Tower for Laparoscopic Endoscopic' Surgery, 36 High Performance Monitors 23 infuzomats, 23 injectomats, 4 defibrilaters, 3 UPS equipment, 1 Ultrasound platform with 4 ultrasound modules B-SCAN. Biometer, UBM, Pahimeter for the LB, and 1 Direct digital RTG imager, 1 Direct digital workstation and 4 DIVAS modality device licenses for the PP2. - Organizing 6 internships by LP in order to transfer know-how between the partners' medical staff for 30 medical staff - Organizing 3 internships by PP2 for 15 internal medical staff of Bekes County Central Hospital On October 31, 2021, the project was successfully finalized. All activities provided in the project were completed (100%). |

| Main outcomes | Deliverables 1) Acquisition of 2 Telemedicine systems; 2) Medical Equipment purchased: 1 Magnetic resonance imaging (MRI), 3 ultrasounds, 1 C-arm, 1 Digital Radiography - scope device, 1 Full 3D Full HD Tower for Laparoscopic Endoscopic' Surgery, 1 Direct digital RTG imager, Direct digital work station, 1 Vacuum Transport System for Laboratory and Medicinal Samples; 5 High Performance Monitors; 5 High Performance Mechanical Ventilation Device; 31 High Performance Monitors; 23 infuzomats; 4 defibrilaters; 3 UPS equipment; 1 Ultrasound platform with 4 ultrasound modules; 4 DIVAS stations; 23 injectomats Results 1) Purchasing and installing the telemedicine systems in Oradea and in Bekes Hospitals 2) Medical equipment purchased, contributing to the endowment of 6 medical departments 3) 6 medical departments modernized and equipped, thus patients benefit from high-quality services / interventions, with reduced recovery time, early identification, prevention and quality treatment of illnesses ensured, easier and quicker accessibility of medical services in the eligible area facilitated, the ”the second opinion” tool became possible through the telemedicine, thus contributing to a balanced system of treatment, which altogether had a positive impact also on anti-discrimination and social inclusion. Indicators 9/a 1 Population having access to improved health services Planned to be reached: Number: 180,000 persons Reached: 176560 by the end of the implementation period 9/a 2 Number of health-care departments affected by modernized equipment Planned to be reached: Number: 6 health-care departments Reached: 6 departments by the end of the implementation period Website/webpage: https://bmkk.eu/korhazunkrol/eu-palyazatok/cbc- hospequip/ |
| --- | --- |