| 3rd Open Call –Normal Project Proposals |  |
| --- | --- |
| Project code | ROHU-387 |
| Project title | AVC –Added Value in Cooperation for stroke situations |
| Priority axes | 4 – Improving healthcare services (cooperating on healthcare and prevention) |
| Investment priority | 9/a - Investment in health and social infrastructure which contributes to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services. Improved preventive and curative healthcare services across the eligible area |
| Implementation period | 74 months (February 01, 2020 – March 31, 2026) The project has been classified as non-finalised according to CM decision no. 271/05.12.2023. The project has not been physically completed by 31.12.2023, therefore the beneficiaries have assumed responsibility for the full achievement of the indicators and objectives from their own resources by 31.03.2026. The project was included in the non-functional project category. |
| Objective | The project’s main objective was to enable the necessary healthcare infrastructural environment for the early and highly detailed diagnosis of cardiovascular diseases among the target area population |
| Partnership | Lead Beneficiary: Szabolcs-Szatmár-Bereg County Hospitals and University Hospital (Hungary) |
|  | Project Partners: PP2: Satu Mare County Emergency Hospital (Romania) PP3: Satu Mare County Administrative Territorial Unit (Romania) |
| TOTAL Budget | Total € 2,707,819.29, out of which ERDF € 2.301.646,39 |
| Summary | Project ROHU-387 aimed to improve the process of clinical activity targeting stroke interventions by developing the stroke-disease-related departments’ infrastructure and knowledge base. Main activities: - Setting up the Stroke Unit, fully equipped (in the existing Neurology department) in Satu Mare, the STROKE centre's operating permit will be obtained by the extended project implementation deadline. - Purchasing the medical equipment for the stroke centres in Nyíregyháza and Mátészalka (64-slice CT equipment with finder workstation, 128-slice CT equipment with finder workstation, cardiovascular ultrasound device and portable TCD ultrasound device). - finalized - Carrying out awareness campaigns (promotional materials, campaign video clips, social media and TV campaigns)- finalized - Development of a common cross-border-area-focused stroke protocol- finalized - Organizing informal training activities (96 stroke-related training hours and 48 cardiology-related training hours)- finalized |
| Main outcomes | Deliverables 1) Specific medical equipment for the stroke centres in Nyíregyháza and Mátészalka (64 Ct equipment with finder workstation, 128 Ct equipment with finder workstation, cardiovascular ultrasound device, portable TCD ultrasound device) purchased (30 medical departments modernized) 2) New Stroke Unit at Satu Mare County Emergency Hospital established 3) Specialized medical equipment and instruments purchased for the Stroke Unit in Satu Mare: Portable/fixed life functions monitors, Holter EKGs, Syringe pumps, Surgical aspirators, EEG/ EKG instruments, Doppler ultrasonograph, Medical ventilators, Astrup blood gas analysers, EMG instrument, Defibrillators, Patient monitoring stations, Vein viewers for vein access, DVL (transcranial Doppler ultrasonograph), etc. 4) Specific medical equipment for the Cardiology and Emergency units in Satu Mare was purchased (2 medical departments modernized) 5) A common cross-border-area-focused stroke treatment protocol developed; 6) 1 public awareness raising campaign in regard to stroke situation organized; 7) 1 website created; 8) 144 hours of informal training were delivered; 9) 1 Awareness raising film created. |

| Main outcomes | Results 1) Raised awareness and better informed population about stroke and its implications and consequences; 2) Better trained personnel in the area of stroke intervention; 3) 32 modernized medical departments, from the two involved hospitals, will provide improved health care services, will reduce the necessity of a longer treatment and rehabilitation period and will facilitate a successful recovery process of patients affected by stroke related diseases, especially in case of the population of the Satu Mare and Szabolcs-Szatmár-Bereg counties. Indicators 9/a 1 Population having access to improved health services Planned to be reached: Number: 903,000 persons Reached: Number: 907,984 9/a 2 Number of health-care departments affected by modernized equipment Planned to be reached: Number: 33 health-care departments Reached: Number: 32 health-care departments |
| --- | --- |