| 3rd Open Call for Proposals |  |
| --- | --- |
| Project code | ROHU-398 |
| Project title | ForTour BHHB Creating and developing a cross border polycentric network for training and support to increase the quality of tourist and handcraft cross-border services in the counties of Bihor and Hajdu Bihar |
| Priority axis | 3 – Improve employment and promote cross-border labour mobility (Cooperating on employment) |
| Investment priority | 8/b - Supporting employment-friendly growth through the development of endogenous potential as part of a territorial strategy for specific areas, including the conversion of declining industrial regions and enhancement of accessibility to, and development of, specific natural and cultural resources. |
| Implementation period | 64 months (March 1, 2019 – June 30, 2024) The project was classified as non-finalised according to CM decision No. 271/05.12.2023. The project was not physically completed by 31.12.2023; therefore, the beneficiaries assumed the responsibility and achieved the indicators and objectives, using their resources, by 30.06.2024. |
| Objective | The main objective was to improve employment in the eligible area by creating training and support centres for the training and/or specialisation of people in the field of tourism, hospitality, and culture. Furthermore, job fairs were organised to strengthen cooperation between local labour market actors in order to improve the correlation between labour supply and demand and the employment situation in the eligible area. |
| Partnership | Lead Beneficiary: Bihor Destination Management Agency (Romania) |
|  | Project Partners: PP2: Körösszegapáti Orthodox Parish (Hungary) PP3: Roman Catholic Bishopric of Oradea (Romania) PP4: Reformed Parish Bihor Episcopate (Romania) PP5: Romanian Orthodox Parish Ioșia-Nord (Romania) PP6: Izbuc Monastery (Romania) |
| TOTAL Budget | € 2,718,105.80 out of which ERDF € 2,310,389.91 Total eligible expenditure certified within the project: € 2,609,320.29 Budget execution: 96.00% |
| Summary | The ROHU-398 project aimed to increase employment in the eligible area by preparing and organising training and specialisation that takes into account endogenous, natural, cultural and human factors, thereby increasing cross-border mobility and supporting economic development. The main activities planned to be implemented were: - Creating and functioning (fully equipped) a cross-border polycentric network of training and support centres for employment in tourism and hospitality, namely: - AMD Bihor Tourism Training Centre for Tourism (equipping and furnishing); - A new cross-border training and support centre for small craftsmen and tourism "Renaissance" Körösszegapáti, including the endowment; - The indoor and outdoor training centre "Episcopia Bihor" (rehabilitating spaces and endowment); - The Centre for Training and Support in Tourist and Cultural Activities "Basilica Minor" Oradea (rehabilitating church pipe organ and endowment); - "Ars Ecumenica" Heritage and Tourism Support Centre for Heritage and Tourism - Iosia, Oradea (rehabilitating spaces and endowment); - A new permanent training centre for traditional crafts and rural tourism "Izbuc-Călugări", including the endowment, finalised by 30.06.2024. - Organising 42 trainings and/or specialisations for 1,101 people in the tourism industry and synergistic fields; - Organizing more than 15 events to promote job opportunities in tourism, hospitality, crafts, local products and gastronomy, such as 2 "Wine and Bread" editions, 6 cyclotourism tour editions, 1 cross-border fair for the promotion of local gastronomic products, 1 Rural Job Fair, 2 Varadinum Nostra-Classical/ church music festivals, 1 Fair promoting local craft products, 1 Fair of Promotion and Landscape Jobs, 1 Eco Food - The gourmet local food event, etc; - Organising 2 workshops, "New technologies and their applicability in tourism marketing" and "Cross-border Tourism at the Beginning of the Third Millennium - Actuality, Trends, Perspectives" in Oradea; - Creating an Integrated Human Resource Management Strategy for Better Personnel Employability Formed and Specialized to Increase the Attractiveness of Bihor and Hajdu-Bihar Tourist Destinations; - Creating a joint online base with the human resources needs of tourism and hospitality - portal www.tourjob.com; - 12 local gastronomy products identified to be certified as local traditional/mountain products and the presentation of these recipes within the 12 short films and the recipe book elaborated; - Elaborating on a Guide for certification as a local gastronomy point. |
| Main outcomes | Deliverables: - 6 training, specialisation and support centres in the tourism industry and related fields (hospitality, culture), of which 4 in the urban environment and 2 in the rural area (1 in Romania, 1 in Hungary); - 1,101 qualified, trained and/or specialised people in the tourism industry and related fields; - 1 integrated human resources management strategy for better integration of trained and specialised personnel in the tourism industry that will increase the attractiveness of tourist destinations in Bihor and Hajdu-Bihar; - 1 joint online base with the human resource needs from the tourism and hospitality domains; - 1 Guide for certification as a local gastronomy point; - 12 local gastronomy products identified and proposed to be certified as local traditional/mountain products - 1 recipe book containing the local traditional/mountain products identified and other recipes. Results: - Improving employment in the cross-border area by training/specialization of human resources, aiming to increase the quality of tourism and hospitality services; - Promotion of local products and employment in the tourist, cultural, and hospitality sectors, through the events organized; - Increasing employment support, through the well-qualified human resources prepared in tourism, culture, traditional crafts, and hospitality domains and through the construction/rehabilitation/ endowment of the centers. Indicators: The Programme Output Indicator is „CO44 Labour Market and Training: Number of participants in joint local employment initiatives and joint training”. Through project ROHU–398, 1,101 persons benefited from trainings /specializations to help them successfully enter the labour market. Website/webpage: https://fortourbhhb.ro/ |