| 1st Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-79 |
| Project title | ROHU TURRIVER Joint Conservation Management and Development of Information Infrastructure of Protected Areas along the Romanian and Hungarian Course of Tur River |
| Priority axis | 1– Protection and sustainable use of common values and resources (Cooperating on natural and cultural resources) |
| Investment priority | 6/c – Conserving, protecting, promoting and developing natural and cultural heritage |
| Implementation period | 32 Months (1st of May 2018- 31st of December 2020) |
| Objective | The project's general objective was to improve the conservation of habitats and species of interest in the natural protected area and to better inform the stakeholders (tourists and the local community). |
| Partners | Lead Beneficiary: Hortobágy National Park Directorate (Hungary) |
|  | Project partner: PP2: Transylvanian Carpathia Society - Satu Mare (Romania) |
| TOTAL Budget | € 643,759.50 out of which ERDF € 547,195.57 Total eligible expenditure certified within the project: € 624,066.26 Budget execution: 96,94% |
| Summary | The project aimed to improve the conservation status of habitats and the species of interest in the project's area. As a result, the visitors to protected natural areas increased, and tourists and the local community were better informed. The main activities implemented within the project: - Organizing a 3-day workshop for the specialists of the two project partners (12 people in total) to harmonize the monitoring methods used in the two countries - Developing 9 harmonized monitoring protocols for the habitats and species proposed for monitoring |

|  | - Carrying out 2 surveys about protected and/or Natura 2000 terrestrial invertebrate species along the Túr in the RO and HU project area - Carrying out 2 surveys about protected fish species and/or Natura 2000 along the Túr in the RO and HU project area - Completion of 2 reports/investigations about bio-amplification and bio-accumulation processes regarding fish and mollusc fauna in the RO and HU project area - Carrying out 2 surveys about the exotic, invasive species of aquatic macroscopic invertebrates along the Túr and neighbouring wet habitats in the area of the Hungarian project RO and HU - Carrying out 2 surveys about exotic, invasive fish species along the Túr and neighbouring wet habitats in the RO and HU project area - Carrying out 2 surveys about protected Natura 2000 macroscopic aquatic invertebrate species along the Túr in the RO and HU project area - Surveying the plant species listed in Annex 2 of the Habitat Directive, designated species of Natura 2000 sites in the RO area of the project - Equipment purchase (1 electric fishing device and accessories, 1 kayak and accessories, 2 canoes and accessories, 2 4x4 vehicles, 1 microscope and accessories, 13 manual binoculars, specialist books, butterfly nets, 1 digital camera, 1 device GPS, 1 ultra- zoom digital camera, 20 cameras with motion sensors, 1 GPS activity tracker, 1 set of rims, 1 tow bar, 1 underbody protection package, 1 set of all-terrain tires, 1 roof bar, 1 boot mat, 1 set of snow chains, 1 bumper, 1 laptop, etc.) - Carrying out 2 surveys about invasive exotic plant species along Túr and the neighbouring floodplains in the RO and HU project area - Developing a digital map (based on GIS) for the botanical study of the habitats in the HU area of the project - Surveying the designated habitats in the Natura 2000 site ROSCI0214 Tur River (Romania). - Surveying the habitats of the Natura 2000 wetlands in the area of the Hungarian project - Carrying out 2 surveys about protected amphibian and reptile species and/or Natura 2000 along the Túr in the RO and HU - project area - Carrying out 2 surveys about the Eurasian otter in the RO and HU project area - Carrying out 2 surveys about bat species in the RO and HU project area - Developing a joint action plan for conservation - Preparing a report on the appropriate places for the placement of bat boxes in the RO and HU area of the project |
| --- | --- |

|  | - Purchasing 76 bat boxes, 36 bat hibernation boxes, 76 breeding boxes, 36 universal bat boxes and 25 bat panels - Placement of 175 bat boxes on the Romanian project site and 70 on the Hungarian project site - Preparation of 8 reports on the degree of occupation of bat boxes by bat colonies in the RO and HU area of the project - TurGO Pocket Guide System Update! And the purchase of a smartphone - Purchasing 3 touch screen desktop kiosks in Romania and 1 touch screen desktop kiosk and 1 tablet in Hungary - Content development for interactive touchscreen kiosks and pocket guidance system - Publication of promotional materials (18,000 leaflets, 200 scientific papers, 600 posters) - Setting up the bat display wall at Cégénydányád Castle - Production of a 5-minute promotional film at the end of the project and four 2-minute promotional films during implementation - On December 31, 2020, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | The main deliverables: 1) To carry out internal surveys, tools and equipment needed for research were purchased (eg. Electric Fishing Machine, electric engine, neoprene fishing clothes, fishfinder radar, kayak and accessories, canoe and accessories, off-road vehicle, stereo microscope and accessories...); 2) To preserve the riparian woodlands and wood pastures biodiversity, 245 artificial bat boxes were placed out in 39 different locations and a bat-presentation wall was installed at the Cégénydányád Castle. 3) For the guiding of tourists who visit the bicycle route developed in the project, a system was made - pocket-guide system TurGO!. The main results of the project are: - 34,571 ha of land with better conservation status. - 9 harmonized monitoring protocols for monitoring habitats and species - 23 surveys/studies/reports on protected fish species, protected invertebrate species, invasive exotic aquatic macroinvertebrate species, invasive exotic fish species, protected aquatic macroinvertebrate species, plant species listed in Annex 2 to the Habitat Directive, exotic plant species, species of bats, reptiles, otter, etc - 1 coordinated action plan for habitat areas (Natura 2000 sites and protected areas designated at the national level) in Romania and Hungary project area - protecting bat colonies in the program area in Romania and Hungary thanks to bat boxes installed in forests - the development of the information infrastructure aimed at tourists by installing 4 tourist information kiosks equipped with a touchscreen and a smartphone application - a Facebook page and informative materials to promote the natural values of the Tur river - 1 promotional film about the project's activities Main output indicator The Programme Output Indicator is CO23 Nature and biodiversity: Surface area of habitats supported to attain a better conservation status. Through the project ROHU-79, 34,571 ha of land attained a better conservation status. Social media: https://www.facebook.com/Tur-River-ROHU-79-720152224775844/ Promotional movie: - https://www.youtube.com/watch?v=ikoKEH3QEww Website/webpage: - https://www.hnp.hu/hu/szervezeti- egyseg/igazgatosag/1374/erdekessegek-es-reszeredmenyek-a-tur- menti-palyazatban https://tur-info.ro/ |