| 2nd Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-200 |
| Project title | CCC Crossborder events for crossborder citizens |
| Priority axis | 6 – Promoting cross-border cooperation between institutions and citizen (Cooperation of institutions and communities) |
| Investment priority | 11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions (ETC-CB). |
| Implementation period | 12 months (1st of December 2018 – 30th of November 2019) |
| Objective | The project’s main objective was to strengthen cooperation between citizens by organizing cultural events in Toboliu, Girișu de Criș, and Nojorid (RO), as well as in Körösnagyharsány (HU). These events celebrated local traditions, fostered closer community ties, and reinforced relationships between the participating communities. |
| Partnership | Lead Beneficiary: Toboliu Commune (Romania) |
|  | Project Partners: PP2: Körösnagyharsány Local Self Government (Hungary) PP3: Girisu de Cris Commune (Romania) PP4: Nojorid Commune (Romania) |
| TOTAL Budget | € 77,000.00, out of which, ERDF € 65,450.00 Total eligible expenditure certified within the project: € 74,764.33 Budget execution: 97.10% |
| Summary | The project ROHU-200 aimed to establish an informal frame and an active interaction between the inhabitants of the four localities and to increase their awareness regarding their specific customs and traditions through participation and involvement in concerts and traditional cooking contests. The main activities implemented within the project: |

|  | - Organization of 4 cooking contests (one by each partner) within the annual traditional festivals: the Cabbage Festival in Toboliu (RO) and Körösnagyharsány (HU), Village Days in Girișu de Criș (RO), and the Autumn Fest in Nojorid (RO), with the participation of contestants from both Romania and Hungary. During the cooking contests, traditional cabbage dishes were prepared and served free of charge to all participants and guests; - Organization of 4 concerts within the annually held festivals in each commune, featuring Romanian and Hungarian artists and bands. - Procurement of equipment to support event organization, including a mobile stage with sound and lighting system, 8 wooden kiosks for the display of traditional products, 3 cooking boilers with stoves, and disposable tableware. The partners’ cooperation within this project led to a strengthened relationship between the four communities and their inhabitants and a population more aware of the cultural traditions. On November 30, 2019, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | Deliverables: - Four cooking contests were organized, one by each partner, within the framework of the Cabbage Festival in Toboliu, the Cabbage Festival in Körösnagyharsány, the Village Days in Girișu de Criș, and the Autumn Festival in Nojorid, with the participation of contestants from Romania and Hungary. - Four concerts were organized, one in each commune, within the above-mentioned festivals, featuring Romanian and Hungarian artists and bands. Approximately 2,000 participants attended each event. - One mobile stage with a convertible roof, including a sound and lighting system, was procured within the project and will be used by all partners for future events. - Seven wooden kiosks, ten sets of wooden benches and tables, and one event pavilion were purchased to support the activities organized within the project and will be jointly used by all partners for future events. Results: - A total of 513 participants from Romania and Hungary took part in joint cultural events, strengthening cross-border community interaction and participation. - • Cross-border cooperation between the four partner communities was reinforced through joint organization of traditional festivals and cultural activities. - • Awareness and appreciation of local traditions were increased among participants, contributing to the preservation and promotion of cultural heritage in the cross-border area. - • Informal interaction between citizens during cooking contests and concerts fostered closer interpersonal relationships and enhanced mutual understanding between the two countries. Indicators: The Programme Output Indicator is „11/b2 Number of people participating in cross-border cooperation initiatives”. Through project activities, 513 people have participated in joint cultural events. |