| 2nd Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-271 |
| Project title | SCTH The Minority Question in the ROHU cross-border area: Slovak Culture, Tradition and History without Borders |
| Priority axis | 6 – Promoting cross-border cooperation between institutions and citizen (Cooperation of institutions and communities) |
| Investment priority | 11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions (ETC-CB) |
| Implementation period | 12 months (1st of December 2018 – 30th of November 2019) |
| Objective | The project's main objective was to promote the traditions, culture and history of the Slovak community in the context of cross-border cooperation. |
| Partnership | Lead Beneficiary: Sinteu Commune (Romania) |
|  | Project Partner: PP2: Organization of Slovaks from Csaba (Hungary) |
| TOTAL Budget | € 71,500.00 out of which ERDF € 60,775.00 Total eligible expenditure certified within the project: € 69,803.51 Budget execution: 97.63% |
| Summary | The project ROHU-271 aimed to enhance the conservation and identity of the cross-border cultural heritage to stimulate the expansion, consolidation and diversification of economic activities related to tourism, cultural activities, entertainment, services, and trade in the area of Șinteu (RO) and Bekescsaba (HU). The main activities implemented within the project: - organizing 2 cross-border workshops regarding "The Slovak Minority Issue", in Sinteu (RO) and in Bekescsaba (HU); |

| Summary | - organizing the “Living Slovak Museum: A Museum of Slovak Culture and Traditions” event in Șinteu and Bekescsaba, where information about Slovak communities and organizations from the cross-border area were collected and presented, along with insights into the Slovak way of life in the past and present, their history, traditions, folk culture, and cuisine.; - acquisition, by both partners, of equipment necessary for event organization: tents, wooden booths, outdoor furniture: benches and tables - development of an online network of communities (set on a website), organizations, institutions, actors, and groups that share a common interest in promoting and preserving Slovak culture and traditions. On November 30, 2019, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | Deliverables: - Two workshops on “The Slovak Minority Issue”, one in Romania and one in Hungary. - Two “Living Slovak Museum: A Museum of Slovak Culture and Traditions” events, gathering and presenting information about Slovak communities and organizations from the cross-border area, including the Slovak way of life in the past and present, history, traditions, folk culture, and cuisine. - Purchase of equipment necessary for event organization, including tents, wooden booths, outdoor furniture (benches and tables), and photo and audio equipment. - Development of an online network of communities, organizations, institutions, actors, and groups with a shared interest in promoting and preserving Slovak culture and traditions, hosted on www.slovakok.hu Results: - Promotion of Slovak traditions, culture, and shared history within the context of cross-border cooperation along the Romanian-Hungarian border. - Enhanced cultural dimension of local fairs and festivals, increasing their cross-border influence and impact, particularly in preserving cultural heritage related to local and traditional products and production processes. Indicators: The Programme Output Indicator is „11/b2 Number of people participating in cross-border cooperation initiatives”. Through project ROHU – 271, 2,467 people have participated in the events dedicated to Slovak culture and traditions, promoted among the cross-border population. |