| 3rd Open Call for Proposals |  |
| --- | --- |
| Project code | ROHU-406 |
| Project title | CROSSGROWING Effective cross-border cooperation for development of employment growths in Arad and Bekes County |
| Priority axis | 3 – Improve employment and promote cross-border labour mobility (Cooperating on employment) |
| Investment priority | 8/b - Supporting employment-friendly growth through the development of endogenous potential as part of a territorial strategy for specific areas, including the conversion of declining industrial regions and enhancement of accessibility to, and development of, specific natural and cultural resources. |
| Implementation period | 58 months (1st of March 2019 – 31st of December 2023) |
| Objective | The project aimed to enhance employment growth by addressing the labour market needs of enterprises and reducing labour shortages. It provided up-to-date information through a dedicated database on investment areas and relevant data, and organized multiple professional events where businesses and investors could connect with potential workforce, while employees could access quality job opportunities on both sides of the border. |
| Partnership | Lead Beneficiary: Bekes County Foundation For Enterprise Development (Hungary) |
|  | Project Partners: PP2: Arad County Chamber of Commerce, Industry and Agriculture (Romania) |
| TOTAL Budget | € 1,125,764.00 out of which ERDF € 956,899.40 |
| Summary | The ROHU-406 project aimed at the personal development of people from the border area, thus contributing to increasing employment, meeting the labour market requirements of enterprises and reducing the labour shortage. At the same time, a database was developed to provide updated information on investment areas and various data of interest (for example locations of properties for sale/rent, industrial parks, free zones, information on taxes and benefits, regulations available in the respective locations). Numerous free professional events were organized on both sides of the border. As a result, labour market stakeholders received information that facilitated access to jobs. The main activities were: - Organization of 37 professional events (22 in Hungary and 15 in Romania) for interested parties - job seekers, companies, and NGOs, the access to these events being free of charge; - Development of a common database that provide updated information on investment areas and various data of interest; - The purchase of equipment to support management teams and the organization of professional events (for both beneficiaries); - Renovation and furnishing with office furniture of the headquarters of the Békés County Foundation for the Development of Enterprises (HU). The total value of the investment was 55,000 euros. |

| Main outcomes | Deliverables: - Professional Events: A total of 35 professional events were organized on both sides of the border. These events provided a platform for presenting good practices to jobseekers, stakeholders, businesses, and NGOs. A total of 3,238 individuals attended the 21 events in Hungary, while 1,851 participants took part in the 14 events held in Romania. - Joint Study: A joint study was conducted to assess the labor market situation in the region and to develop a shared regional development strategy. - Investment Area Database: A comprehensive database was created to identify potential investment areas within the region. - Project Website: A dedicated project website was developed, offering a free database with essential information for both sides of the border, available in Hungarian, Romanian, and English. The website can be accessed at: https://ipariingatlanrohu.hu/, https://spatiindustrialerohu.ro/, and http://industrialestaterohu.eu/. - Office Renovation and Furniture Procurement: The BVVA office was renovated and furnished. The renovation was completed ahead of schedule, as it did not require a building permit. Early completion allowed the office to function for project meetings and engagement with target groups. Renovation works included demolition, electrical installations, technical building work, plastering, masonry, flooring, insulation, painting, and renovation of doors and windows. - Equipment for Professional Events: CCIA acquired all equipment necessary for organizing professional events. Results: 1.The project supported border residents by fostering employment growth through the organization of professional events in both countries, which were offered free of charge. This initiative ensured that everyone interested had access to valuable resources and opportunities. 2.The renovation and proper equipping of the office enabled BMVA to carry out its activities efficiently. Indicators: The Programme Output Indicator was „CO44 Labour Market and Training: Number of participants in joint local employment initiatives and joint training”. Through the ROHU - 406 project, the number of participants involved in the project in the field of the labour market and economy, job creation through events, database development and other activities was 5,029 people. Website/resources: https://industrialestaterohu.eu/ https://ipariingatlanrohu.hu/ https://spatiindustrialerohu.ro/filme-promo/ https://interreg-rohu.eu/wp- content/uploads/2021/04/ROHU406_Professional_study_HU_1.hp.pdf |
| --- | --- |