| 3rd Restricted Call for Proposals - Full Application Form |  |
| --- | --- |
| Project code | ROHU-445 FAF |
| Project Title | CBC Incubator Romanian-Hungarian cross-border cultural incubator for performing arts |
| Priority Axis | 1 - Joint protection and efficient use of common values and resources (Cooperating on common values and resources) |
| Investment priority | 6/c - Conserving, protecting, promoting and developing natural and cultural heritage |
| Implementation period | 55 months (June 01, 2019 – December 31, 2023) |
| Partnership | LB: Csokonai Theatre (Debrecen, Hungary) PP2: Municipality of Debrecen (Hungary) PP3: Szigligeti Theatre (Oradea, Romania) |
| Project budget | Total 12,841,586.99 EUR, out of which ERDF 10,834,325.06 EUR LB: 496,610.97 EUR ERDF, 58,418.98 EUR national co-financing PP2: 9,030,223.88 EUR ERDF, 1,062,273.05 EUR national co-financing PP3: 1,307,490.21 EUR ERDF, 199,937.41 EUR national co-financing |
| Objective | The CBC Incubator project aimed to establish a joint common space in the Romanian-Hungarian border area that connects cultural institutions, artists and cultural professionals, primarily in the field of theatre art. |
| Contribution to indicators | No. of visits to supported sites of cultural and natural heritage and attractions: 18,462 |
| Summary | Justification – common challenges: - Lack of providing appropriate infrastructural and professional background for protecting, developing and sharing common values of performing arts; - Limited level of interconnection between theatres operating in the border area. Project main activities: - Increasing by 18,462 the number of expected visits by creating a Romanian-Hungarian Cross-border Cultural Incubator for Performing Arts in Debrecen, modernizing the theatre technology of Szigligeti Theatre, delivery of joint cross-border cultural activities coordinated by the Csokonai Theatre in Debrecen. |

| Main outcomes | The main deliverables: 1) 6 theoretical training programmes, 16 exchanged performances, 1 archive of performances, 7 “Actors and their languages” workshops, 15 translation workshops, two „2 countries – 2 theatre cultures” conference, one interactive exhibition, 8 acting workshops 2) Complex development of the Szigligeti Theatre in Oradea (reconstruction of stage infrastructure, machinery, technological and functional systems, fire protection infrastructure). 3) Series of online events organized by Csokonai Theatre 4) Newly created Romanian-Hungarian Cross-border Cultural Incubator for Performing Arts in Debrecen (a multifunctional cultural institution with variable and flexible stage technology) Investments - Municipality of Debrecen (PP2): established the new Romanian- Hungarian Cross-border Cultural Incubator for Performing Arts, by demolition/reconstruction and building works, according to its function of multifunctional cultural institution and the endowment with stage technology systems (revolving stage and overhead stage machinery, modern effect lighting and audio system), elevators, utility systems, interior fixed furniture etc. The core function of the building (4796.22 sqm at 8 levels) is ensured by the main stage, including an auditorium for 350 audiences, thus creating a special arena-like space, making the hall ideal for staging musical plays. The value of the investment: 5 million euros. - Szigligeti Theatre (PP3) aimed the infrastructural development of the stage space and stage technology of the Oradea State Theatre, which provides a venue for Szigligeti Theatre company. The complex development ensures greater flexibility for cultural performances and comprises the reconstruction of stage infrastructure including renovation of stage basement and floor as well as the electrical and plumbing installation, assembly of machinery, technological and functional systems including revolving stage, battens for stage lighting, stage lighting, curtain control and audio-visual stage management systems. Total value of the investment: 1.02 million euros. The three partners cooperated to create a sustainable RO-HU cultural network, focused particularly on the theatre cultures, by supporting amateur theatres through organising 14 workshops, a series of 16 performances exchanged with the participation of different theatres from the Romanian-Hungarian border area, establishing a theatre archive and creating an interactive exhibition of theatre cultures, organizing 7 actors and 15 translation workshops. Total value: 0.48 million euros. The main results: 1) Improved conditions for sharing, creating, protecting and promoting the common cultural values 2) Increased cultural mobility in the eligible area 3) Greater flexibility for cultural performances 4) Higher tourist attractiveness of the Romanian-Hungarian Cross-Border area 5) A strengthened link between cultural organizations/professionals, which will contribute to promote the cultural diversity , intercultural dialogue, will stimulate creativity and will contribute to the enrichement of both cultures (RO and HU). The main indicators: The project ROHU445 contributes to the Programme Output Indicator CO09 Sustainable Tourism: Increase in the expected number of visits to supported sites of cultural and natural heritage and attractions, the number of tourists visiting the supported cultural and natural sites and attractions increased by 18,462. Project website: https://www.cbcincubator.hu/ |
| --- | --- |
| Concept Note | Project code: ROHU-343 Implementation period: August 01, 2018 – January 31, 2019. Total budget 46,180.00 EUR, out of which ERDF 39,253.00 EUR. Preparation activities for developing the Full Application Form. |