| 2nd Restricted Call for Proposals - Full Application Form |  |
| --- | --- |
| Project code | ROHU-450 FAF |
| Project Title | DESP - Development and Testing of Efficient Screening and Prevention Programs |
| Priority Axis | 4 – Improving health care services (Cooperating on health care and prevention) |
| Investment priority | 9/a – Investment in health and social infrastructure which contributes to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services. |
| Implementation period | 53 months (August 01, 2019 – December 31, 2023) |
| Partnership | LB: Csongrád-Csanád County Health Care Center – Hódmezővásárhely-Makó (Hungary) PP2: Association of Vincentian Sisters of Charity (Romania) |
| Project budget | Total 13,007,120.56 EUR, out of which EDRF 11,056,052.47 EUR LB: 8,669,289.15 EUR ERDF, 1,529,874.56 EUR national co-financing PP2: 2,386,763.32 EUR ERDF, 365,006.32 EUR national co-financing |
| Objective | The main overall objective of the project was to mitigate the morbidity and mortality rates of cancer and circulatory diseases, by increasing the efficiency of screening and to strengthen preventive healthcare and health awareness in the region. |
| Summary | Project main activities: - LB: extension of Csongrád-Csanád County Health Care Center — Hódmezővásárhely-Makó, with two extra floors housing the Internal Medicine Department and Paediatrics; - PP2: improving the diagnostic and screening capacities of already existing facilities as well as preterm child care and screening in the Blessed János Scheffler Center; - LB, PP2: make a significant investment in equipment to allow efficient screening, diagnostic, and curing activities. - LB, PP2: various screening programs running in both locations (but also with well-equipped screening buses and in rural areas) to enlarge the proportion of the population that has been screened. The partners also contributed to developing a new solution involving the elaboration of a joint monitoring and evaluation system and to running a series of professional training and communication activities, covering a wide range of topics, tools and targeting different groups. |

| Main outcomes | Deliverables 1) New medical equipment purchased for: - 7 departments of HMEK in Hódmezővásárhely and Makó, namely: Dermatology, Mammography, Pulmonology, Pathology, Paediatrics, Cardiology and Gastroenterology - 6 departments from “Hám János Medical Centre” in Satu Mare, namely: Cardiology, Mammography/ Oncology, Dermatology, Gastroenterology, Urology and Blessed János Scheffler Centre for screening Preterm Infants. One of the most notable results on the Romanian side is the mobile mammography unit included in the National Brest Cancer Screening Programme, coordinated in the region by the Oncological Institute in Cluj-Napoca. - 2 Health Development Offices, one in Hódmezővásárhely and one in Makó 2) Two additional floors built at the Hódmezővásárhely hospital, for the Paediatrics and Internal Medicine departments 3) Training sessions for specialists, connected to the new equipment purchased within the project 4) 52 Information & Awareness raising Events: 12 Open Events for the population of Hódmezővásárhely and Makó, respectively 4 Workshops for General Practitioners (Family Doctors) and their assistants, respectively 36 events on the importance of regular screenings, living a healthy lifestyle, caring for children / preterm infants in Satu Mare. 5) 9 screening programs carried out in 6 different areas: Dermatologic, Cardiovascular, Mammographic, Pulmonologic screenings, Gastroeneterologic and Preterm Infants screenings Results 1) Efficient screening and prevention programs were elaborated, tested and implemented, on both sides of the border. 2) Improved diagnostic and therapeutic background in the area addressed by the project is achieved, by the new operating medical equipment and new hospital sections in. 3) A larger number of population has access to improved health services. 4) The addressed health care facilities provide better medical services, and therefore ensure a better quality of the health-care services for the population in the area addressed by the project. Indicators 9/a 1 Population having access to improved health services Planned to be reached: Number:1139644 persons Reached: Number: 1036141 9/a 2 Number of health-care departments affected by modernized equipment Planned to be reached: Number: 15 health-care departments Reached: Number: 15 health-care departments Social media: https://www.facebook.com/csmek.rohu |
| --- | --- |

| Concept Note | Project code: ROHU-240 Implementation period: September 01, 2018 – February 28, 2019 Total budget 341,753.00 EUR, out of which ERDF 290,490.05 EUR. Preparation activities for developing the Full Application Form. |
| --- | --- |