| 2nd Restricted Call for Proposals - Full Application Form |  |
| --- | --- |
| Project code | ROHU-457 FAF |
| Project Title | ROcHUs - Care for health in Satu Mare and Szabolcs-Szatmár-Bereg counties |
| Priority Axis | 4 – Improving health care services (Cooperating on health care and prevention) |
| Investment priority | 9/a – Investment in health and social infrastructure which contributes to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services. |
| Implementation period | 61 months (August 01, 2020 - August 31, 2025) The project has been classified as non-finalized according to MC decision no. 271/05.12.2023, because it has not been physically completed by 31.12.2023, later the project was included in the list of non-functional projects. The project implementation period was repeatedly extended in order for the LB - Satu Mare County Emergency Hospital to physically fully complete both investments components (2 pcs. wastewater pre-treatment bases and glazing refurbishment of the Old Hospital building), while related costs had to be supported from own funds of the beneficiary. The project was fully implemented on 31.08.2025, in line with the presented objectives and output indicators. |
| Partnership | LB: Satu Mare County Emergency Hospital (Romania) PP2: Satu Mare County Administrative-Territorial Unit (Romania) PP3: Szabolcs-Szatmár-Bereg County Hospitals and University Hospital (Hungary) PP4: Hospital of Felső-Szabolcs ( Hungary) |
| Project budget | Total 6,205,884.28 EUR, out of which EDRF 5,275,001.63 EUR LB: 3,601,127.73 EUR ERDF, 3,060,132.47 EUR national co-financing PP2: 0.00 EUR ERDF, 0.00 EUR national co-financing PP3: 1,497,471.10 EUR ERDF, 1,272,882.43 EUR national co-financing PP4: 1,107,285.45 EUR ERDF, 941,192.63 EUR national co-financing |
| Objective | The project aimed to bring radical improvement in the general conditions of the healthcare system in Satu Mare and Szabolcs-Szatmár-Bereg counties. |
| Contribution to indicators | 9a/1 Population having access to improved health services: 907,984 pers. 9a/2 No. of healthcare departments affected by modernized equipment: 10 |
| Summary | Project main activities implemented: - LB: purchasing medical equipment to improve the quality of the medical services in 7 departments, installing wastewater pre- treatment plants in both locations of SMCEH and refurbishment glazing at the Old Hospital of Satu Mare. - PP3 and PP4: purchasing medical equipment for emergency interventions in heart disease, improving the quality of the medical services in 3 medical units |
| Main outcomes | Deliverables 1) Procured and installed medical instruments in the Vascular Center of Szabolcs-Szatmár-Bereg County Hospitals and University Hospital 2) Reduced door-to-balloon times by procuring performant medical instrumentation in the Vascular Center of Szabolcs-Szatmár-Bereg County Hospitals and University Hospital 3) Refurbished and equipped general laboratory in Hospital of Felső-Szabolcs 4) Developed cross-border tele-diagnose network and new instrumentation put in function in the two county hospitals located on both sides of the border 5) Better trained medical specialists thanks to the annual Cross-border Medical Conference organized in Satu Mare 6) 7 departments of Satu Mare County Emergency Hospital endowed with medical equipment Results 1)Enhanced medical service level in 7 departments of Satu Mare County Emergency Hospital 2)Enhanced medical service level in 2 units of Szabolcs-Szatmár-Bereg County Hospitals and University Hospital 3)Enhanced medical service level in 1 unit of Hospital of Felső-Szabolcs 4)Access to improved health services for the population of Satu Mare and Szabolcs-Szatmár-Bereg counties. |
| Concept Note | Project code: ROHU-245 Implementation period: September 01, 2018 – February 28, 2020 Total budget 349,757.11EUR, out of which ERDF 297,293.54 EUR. Preparation activities for developing the Full Application Form. |