| 1st Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-10 |
| Project title | VOLUNTEER Joint development of the voluntary emergency response and disaster management capacity in the eligible border area |
| Priority axis | 5 – Improve risk-prevention and disaster management (Cooperation on risk prevention and disaster management) |
| Investment priority | 5/b – Promoting investment to address specific risks, ensuring disaster resilience and developing disaster management systems |
| Implementation period | 30 Months (April 01, 2018 – September 30, 2020) |
| Objective | The project’s main objective was to increase the capacity of preparation and intervention for the voluntary units in the Bihor and Hajdú-Bihar counties. The project improved cross-border risk and disaster management by strengthening an essential segment of the response system: voluntary fire brigade units. |
| Partnership | Lead Beneficiary: Association for Business Promotion in Romania (Romania) |
|  | Project Partners: PP2: Diosig Commune (Romania) PP3: Firefighter Federation of Hajdú Bihar County (Hungary) |
| TOTAL Budget | € 1,406,367.00, out of which ERDF € 1,195,411.95 Total eligible expenditure certified within the project: € 1,376,209.18 Budget execution: 97,86% |
| Summary | ROHU-10 project aimed to use the exchange between cross-border organizations to strengthen the capacity of volunteer-based firefighting organizations. Thus, exchanging experience, the transfer of know-how, and the joint intervention exercises created and supported a cross-border cooperation mechanism between the volunteer firefighters from the two counties. The main activities implemented within the project: - Construction of the training centre in the Diosig commune, fully equipped and a wood-fired training simulator container - Purchasing equipment for practical training (20 sets of Firefighter equipment for training, 6 sets of Breathing protection, 1 set of equipment used for the firefighting contests, 1 set of accessory equipment for practising intervention with water and foam, 1 set of accessory equipment for breaking in and demolishing, 1 air compressor, 1 set of First-aid equipment etc.) - Organizing training for volunteer firefighters from Romania at the end of which 138 firefighters had a firefighter diploma according to Romanian legislation; - Purchasing equipment (1 water tanker, 1 power generator, 1 set of First-aid, extrication and breathing protection kits and 6 sets of firefighter equipment) for the volunteer emergency service in Diosig; - Hiring 5 people in the Diosig emergency volunteer service (1 head of service and 4 tanker drivers) and obtaining written commitments from the volunteers who will serve the center in Diosig; - Developing a set of protocols and procedures for regulating the organization and the interventions of the volunteer emergency service in Diosig; - Procurement of the equipment to support the implementation of specific activities (firefighting demonstration kit, respiratory protection demonstration kit, IT equipment for presentations) for the Hajdú Bihar Fire Brigade Federation; - Organizing an interactive caravan on the Hungarian side to increase the population's awareness of the importance of volunteer firefighting units (20 interactive public demonstrations at public events in the border area). For the same purpose, 4 short videos were also made (http://hajdu.tuzoltoszovetseg.hu/content/rohu10-filmek); - Organizing training courses for volunteer firefighters in Hungary for both advanced and beginners, where 192 participants were certified, receiving diplomas issued by the Directorate for Disaster Management in Hungary (92 in the course for beginners and 96 for advanced); - Developing an e-learning platform and a mobile application for an emergency alarm. The app is available free of charge to all voluntary emergency services on both sides of the border; On September 30, 2020, the project was successfully finalized. All activities provided in the project were completed (100%). |
| Main outcomes | The main deliverables of the project are: 1) Sets of equipment used for the firefighting contests and for firefighters' training purchased. 2) 1 training programme for the professional standard of firefighters was organized. The training had a theoretical module composed of general firefighting training (40 h) and a course for developing competences in using the specific machines during interventions. 3) 1 Multifunctional Training Center for firefighters was built in Diosig, serving for providing theoretical and practical trainings to the voluntary firefighters from the two countries, and also as a headquarters for the voluntary emergency service unit from Diosig. 4) Purchase of 1 Water tanker truck equipped with all the necessary accessories specific for interventions in cases of fire, in line with the provisions of the national legislation (for Diosig intervention center); 5) 1 set of protocols and procedures have been developed, for regulating the organization and the interventions of the voluntary emergency situation service; 6) 18 interactive public demonstrations were organized to increase awareness about the voluntary firefighting units and the prestige of this noble vocation within the local population. 7) 1 E-learning platform was developed, containing the most important information needed for a volunteer firefighter during his work. The main results of the project are: 1) A functional Training Center for firefighters, newly built and well equipped, which facilitates access to theoretical and practical training for the voluntary firefighters from the two countries. 2) A functional fire extinguisher vehicle, allowing a better emergency response in case of fire in the Diosig Commune area. 3) A set of protocols and procedures for voluntary emergency services, regulating the organization and the interventions of the voluntary emergency situation service in Diosig Commune, incorporating the newest professional standards, developed based on the requirements of the national legislation, thus serving as a best practice model for other localities. 4) A prepared corps of voluntary firefighters in Hajdu-Bihar and Bihor counties and an increased capacity and preparedness of the voluntary emergency intervention units, enhancing the quality of the overall emergency response system in the Programme Area. 5) An approved training programme for firefighters, which provided 105 voluntary firefighters with the necessary information and practice for better preparedness in case of fire. 6) Population from the targeted area is better protected in case of emergency situations, due to investments in infrastructure, equipment, and training realized within the project. The output indicator: The Programme output indicator is 5/b1 “Population safeguarded by improved emergency response services”. Through project ROHU-10, 437,238 people are better protected against disasters by improved emergency response services. Social media: https://www.facebook.com/profile.php?id=100063714451357 Website/webpage: https://trainingcenter.biz |