| 2nd Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-280 |
| Project title | Co-cultured Cultural Cooperation among Citizens from the Salonta-Gyula Cross- border Area |
| Priority axis | 6 – Promoting cross-border cooperation between institutions and citizen (Cooperation of institutions and communities) |
| Investment priority | 11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions (ETC-CB). |
| Implementation period | 12 months (1st of November 2018 – 31st of October 2019) |
| Objective | The project’s main objective was to promote cultural diversity and common traditions through artistic events, organized in Salonta (RO) and Gyula (HU). |
| Partnership | Lead Beneficiary: The Municipality of Salonta (Romania) |
|  | Project Partners: PP2: Gyula town (Hungary) |
| TOTAL Budget | € 80,000.00, out of which, ERDF € 68,000.00 Total eligible expenditure certified within the project: € 78,811.29 Budget execution: 98.51% |
| Summary | The project ROHU-280 aimed to enhance the attractiveness of the Bihor-Békés cross-border region, through a diverse intercultural approach related to arts: films, theatre, and handicrafts. The project brought an innovative character through the rediscovery and exploitation of local resources and joint heritage. The main activities implemented within the project: - organization of several cultural events in Salonta (RO) for people of both sides of the border, providing opportunities for participants to meet, interact and strengthen cross-border connections.: “Long Night of Museums”, theatre festival, “Evening seating” (sezatoare) of local people with traditional singing and a film-screening; |

|  | - creation on behalf of PP2 of a film with the participation of amateur actors in Gyula (HU). The film was featured in both partner cities and was submitted to various national and international film competitions and festivals. - Purchasing new equipment (1 laptop, 1 video projector, 1 projection screen) to ensure the availability of the equipment for the event and the roaming caravan on the Romanian side of the border, as well as a better quality of the broadcasting. On October 31, 2019, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | Deliverables: 1. Organization of cultural events in Salonta (Romania) involving participants from both sides of the Romania–Hungary border (Salonta and Gyula): - “The Long Night of Museums” – held on 18 May 2019, when local museums joined the international initiative Night of Museums. - Theatre Festival – organized in Salonta on 21–22 June 2019, with the participation of the Kalocsai Theatre, which presented two performances: Grand Operetta (21 June 2019) and Hippolyt the Lackey (22 June 2019). - Traditional community gathering (“șezătoare”) – held on 22 June 2019 in Salonta to promote local traditions. The event included traditional song recitals (doina) and various activities such as sewing, knitting, crocheting, glass painting, drawing, corn cob cleaning and traditional dancing (hora). - Cross-border Film Festival – organized between 23–25 August 2019 at the Arany János Museum, where six films with cross-border themes and local relevance were screened, followed by thematic discussions. - Presentation and promotion of the film created in Gyula, which was screened during the project in Salonta, Oradea and Gyula. 2. Joint cross-border cultural activities in Gyula: - A film featuring Toldi as the main character was jointly produced in Gyula with the participation of amateur actors. - The film production involved 50 staff members, and the screening was attended by at least 500 spectators from Salonta and Gyula. 3. Overall, 4,927 people from the Romania–Hungary cross-border area (Gyula and Salonta) participated in the project activities. |

|  | Results: - Strengthened cross-border connections between the communities of Salonta (Romania) and Gyula (Hungary) through joint participation in cultural events organized in both towns. - Improved preservation and promotion of cultural diversity and shared traditions in the Bihor–Békés cross-border area through cultural events highlighting local history, traditions, arts and heritage. - Active involvement of young people in cultural activities, contributing to the development of a new generation of promoters of cross-border cooperation in the fields of local heritage, traditions, culture, and arts. Indicators: The Programme Output Indicators were: “11/b1 Number of institutions directly involved in cross-border cooperation initiatives” and „11/b2 Number of people participating in cross-border cooperation initiatives”. Through project ROHU–280, 2 institutions were directly involved in cross-border cooperation and 4,927 people have participated in cultural events organized within the project. Social media: https://www.facebook.com/events/co-cultured-rohu280/festivalul-filmului-pe-frontier%C4%83-hat%C3%A1rmenti-filmek-fesztiv%C3%A1lja/391167661524734/ |
| --- | --- |