| 2nd Open Call – Normal Projects |  |
| --- | --- |
| Project code | ROHU-281 |
| Project title | „Heritage of Csanád, bridge of schools” - cross-border cooperation of Catholic schools |
| Priority axis | 6 – Promoting cross-border cooperation between institutions and citizens (Cooperation of institutions and communities) |
| Investment priority | 11/b, Promoting legal and administrative cooperation and cooperation between citizens and institutions |
| Implementation period | 24 months (1st of January 2020 – 31st of December 2021) |
| Objective | The main objective of the project was the promotion of the values of the neighbouring Békés-Banat regions as ethnographic, cultural and geographical landscapes to the local population. |
| Partnership | Lead Beneficiary: Savio Saint Dominic Catholic Elementary School and Nursery School (Hungary) |
|  | Project Partner: PP2: Jimbolia Secondary School (Romania) |
| TOTAL Budget | € 210,350.00, out of which, ERDF € 178,797.50 Total eligible expenditure certified within the project: € 190,153.70 Budget execution: 90.39% |
| Summary | Through the ROHU-281 project, the partners aimed to create spaces attached to schools, where the traditions of the cross-border area can be studied, both by children and adults, and in where joint events can be organized. The main activities implemented within the project: - creation of 2 community spaces with stages for performances and concerts; - organization of arts-and-crafts and folk-art courses for 3000 children and parents; - organization of 6 joint events, presenting common traditions. On December 31, 2021, the project was successfully finalized. All activities provided in the project were completed (100%). The cooperation between the partners in this project gave them the opportunity to organise joint cultural programmes, to get to know each other's particularities, traditions and values, and to contribute to the strengthening of the local economy. The Programme Output Indicator is „11/b1 Number of institutions directly involved in cross-border cooperation initiatives”. Project ROHU – 281 contributes to this indicator by reaching a number of 2 institutions directly involved in the joint activities |
| Main outcomes | Deliverables 1. Creation of Cross-Border Cultural Spaces: The partners aimed to establish spaces attached to schools where the traditions of the cross-border area could be studied by both children and adults, as well as hosting joint events: -LB HU: A community space was converted (95 m²), including courtyard pavement and a new outdoor stage for performances and concerts (150 m²). -PP2 RO: The school’s ceremonial room was renovated, and a 32 m² indoor stage was constructed. 2. Local Courses and Events Organized by LB HU Savio: -110 Enamel Art Courses for pupils (1-3 classes/week), led by a Master of Folk Arts, with necessary equipment purchased. -150 Folk Dance Courses for pupils (3-4 classes/week), led by professional dancers, with necessary equipment purchased (folk dance costumes, stage sound system, camcorder, laptop, CD player). -National Attire Presentation: A school event with 118 pupils participating, held on 27 April 2021. -Spice and Herb Garden Setup in the schoolyard, with related equipment acquired. -Sustainability Days on the topic of herbal gardens, organized from 1 to 3 June 2021, with 395 pupils participating. The necessary equipment was purchased (composter, hand tools, leaf blower, lawnmower). -Open-Air Stage Ceremony: A hand-over ceremony for the new outdoor stage, held on 14 June 2021, with the entire pupil community of 146 participants. Equipment purchased included outdoor chairs. 3. Cross-Border Events Organized by LB HU Savio: -Christmas in Békéscsaba, 26 November 2021: A one-day event with 20 teachers (10 from Jimbolia and 10 from Békéscsaba) and 44 students (24 from Jimbolia and 20 from Békéscsaba). -Experts' Day in Békéscsaba, 14 December 2021: A one-day event with 40 teachers (20 from Jimbolia and 20 from Békéscsaba). -Cavalcade in Békéscsaba, 11 October 2021: A one-day event with 20 teachers (10 from Jimbolia and 10 from Békéscsaba) and 40 students (20 from Jimbolia and 20 from Békéscsaba). 4. Local Courses and Equipment Purchased by PP2 RO Gimnaziala Jimbolia School: -Icon Painting Courses for Children: 20 courses, each attended by 20 children. -Skilful Hands Courses: Organized 20 times, each attended by 20 children. -Folk Dance Courses: 20 courses, with 40 children participating per event. -Gardening Event: 82 pupils participated in planting 162 plants in the vertical garden. 5. Cross-Border Events Organized by PP2 Jimbolia: -Cultural Cavalcade in Jimbolia, 27 September 2021: A one-day event with 20 teachers (10 from Jimbolia and 10 from Békéscsaba) and 40 pupils (20 from Jimbolia and 20 from Békéscsaba). -Exchange of Good Practices for Promoting Local History, 15 December 2021: A one-day event attended by 20 teachers from each school, Jimbolia and Békéscsaba. -Study Tour, 23-24 August 2021: A two-day event attended by 20 teachers from each school, Jimbolia and Békéscsaba. 6. Equipment Purchased by PP2 Jimbolia: -Audio and video equipment -Vertical herb garden with accessories -Folk costumes -Tables, chairs, cabinets Results: 1) A better access of the population to community spaces, through the transformation of unused buildings into functional public event spaces. 2) Better cooperation between communities, through the development of arts and crafts and other traditional arts courses. 3) The two schools learned from each other’s best practices and adapted them in their own institutions. Both partners created a community space attached to the school where they perpetuate the collected traditions to school-age children and adults and where they can organise joint events. |