|  | 2nd Open Call -Normal Projects |  |  |
| --- | --- | --- | --- |
| Project code |  | ROHU-300 |  |
| Project title |  | ProTourism Common challenges - common solutions: institutional development in the field of tourism |  |
| Priority axis |  | 6 – Promoting cross-border cooperation between institutions and citizen (Cooperation of institutions and communities) |  |
| Investment priority |  | 11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions |  |
| Implementation period |  | 18 months (December 01, 2018 – May 31, 2020) |  |
| Objective |  | The project’s main objective was to intensify the collaboration between the three local public authorities in the field of tourism promotion. |  |
| Partnership |  | Lead Beneficiary: Municipality of Jimbolia (Romania) |  |
|  |  | Project Partners: PP2: Carpinis Commune (Romania) PP3: Municipality of Csanadpalota (Hungary) |  |
| TOTAL Budget |  | € 209,368.00, out of which ERDF € 177,962.80 Total eligible expenditure certified within the project: € 179,950.68 Budget execution: 85.95% |  |
| Summary |  | The project ROHU-300 aimed to develop the institutional capacity of the participating local public administrations from 3 perspectives: development of human resources, development of infrastructure and development of tourism materials. The main activities implemented within the project: - development of human resources, through 4 workshops and exchange of best practices between the 3 localities; |  |

|  | - development of tourism infrastructure, through the acquisition of equipment and small-scale renovation works of the 3 touristic Info- centers in Jimbolia, Carpinis (both in RO) and Csanadpalota (HU), - developing tourism materials, used in the promotion of the cross- border region (2700 brochures, 1900 CD album) ; - developing a Joint tourism-promoting strategy - organizing public meetings in Jimbolia, Carpinis and Csanadpalota with the participation of 30 persons from every locality The partnership between the three local public administrations resulted in improved professional relationships and the establishment of appropriate tourist infrastructure, with an emphasis on promoting tourism in the region. On May 31, 2020, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | Deliverables: 1) Joint professional activities organized for 9 people (persons from staff) in order to gain new skills and knowledge in the tourism field; 2) 3 workshops were organized, with the theme of tourism entrepreneur skills; 3) 3 tourist info centers were created and equipped, one by each partner, which function as a unit of each institution; 4) 3 public meetings in the field of rural tourism development and promotion; 5) 1 Joint tourism promoting strategy; 6) 4600 promotional materials consisting of presentation albums with CD and brochures of the three localities where the project is implemented: Jimbolia, Carpinis and Csanadpalota, and a presentation film, to promote tourist attractions of each area. Results achieved: 1) Development of the human resources of the three institutions involved in the project, through workshops and exchange of best practices. 2) Strengthened cooperation between the participating local public administrations through the thematic workshops organized, which focused on tourism entrepreneur skills, rural tourism development and tourism promotion, including IT skills. 3) Promotion of the touristic attractions and the touristic services, through the 3 touristic information centers created, which function as units of the institutions. 4) Development of tourism promotional materials, which will be used in the promotion of the region. Contribution to the Programme indicators: The Programme Output Indicator is „11/b1 Number of institutions directly involved in cross-border cooperation initiatives”. Project ROHU-300 contributed by reaching a number of 3 institutions from Romania and Hungary that were directly involved in the cross-border cooperation. |