| 1st Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-48 |
| Project title | DIRCCES Development of an integrated response capacity to cross-border emergencies |
| Priority axis | 5 - Improve risk-prevention and disaster management (Cooperation on risk-prevention and disaster management) |
| Investment priority | 5/b- Promoting investment to address specific risks, ensuring disaster resilience and developing disaster management systems. |
| Implementation period | 21 Months (October 1, 2019 - June 30, 2021) |
| Objective | The DIRCCES project’s overall objective was to enhance the safety level of the populations from the cross-border region and thus, reduce the social, economic and environmental costs of natural disasters in this territory. |
| Partners | Lead Beneficiary: Town of Aleşd (Romania) |
|  | Project Partners: PP2: Şinteu Commune (Romania) PP3: Szarvas Town Self-Government (Hungary) |
| TOTAL Budget | € 485,400.00 out of which ERDF € 399,532.74 Total eligible expenditure certified within the project: € 444,327.65 Budget execution: 91.54% |
| Summary | The project aimed to generate a large set of effective practices that can be used by project partners and other actors in the emergency field, to ensure more effective future responses to possible cross-border disasters. The main activities implemented within the project: - Purchasing equipment necessary in emergency interventions (1 generator 180KW, 2 professional motor pumps, 2 generators 10 KW, 10 inflatable dams) - LB - Purchasing 3 emergency vehicles (1 4x4 Intervention car, 1 backhoe loader and 1 tractor with a front blade, salt spreader, tipping trailer, scooper and vegetation chopper) - LB - Purchasing 374 emergency tools (e.g. mattresses, beds, military tents, rubber boots, raincoats, electric cable roll, safety helmets, climbing ropes, chainsaws, sliding scales, towing/hauling cable, etc.) – LB - Purchasing equipment (1 tractor with 1 snow thrower, 1 snow plough, 1 salt spreader, 1 front loader, 1 hydraulic winch, 1 chopper, 2 pairs of chains for wheels (front and rear) that will be attached to this tractor, 3 chainsaws and 1 tow/trail) for emergency activities - PP2 |

|  | - Purchasing equipment for emergency activities (1 4x4 intervention car, 1 tipper trailer, 2 pumps, 2 sludge pumps, 2 generators, 1 multi-purpose machine, 1 channel video inspection camera, 1 military tent) – PP3 - Organizing 1 joint event in Aleșd on the topic of risk and disaster management, with 6 activities and 25 participants – LB - Elaboration of the Joint cross-border regional-level Strategy for disaster risk reduction, as guidance for the communities from the cross-border area involved in emergency and risk situations management, in Romanian and Hungarian and translating it into Slovak - LB - Organizing a specific joint event that consists of 4 activities with simulations and drills for 40 people in Sinteu - PP2 - Organizing 5 Info Days in Szarvas for approx. 500 participants, where 10,000 information sheet agenda is disseminated-PP3 - Organizing a 2-day study tour for knowledge transfer for 15 participants - PP3 - Elaborating promotional materials (1000 brochures, 1000 flyers, 500 leaflets, 1 poster, 200 stickers, 400 pen drives, 1 roll-up banner, 8 adds to be published in the local press, 1 homepage) On June 30, 2021, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | The main deliverables: 1) 2 joint events in Alesd and Şinteu and 5 Info days in Szarvas to have communities with a higher level of awareness regarding risk prevention and disaster response 2) Equipment for emergency response purchased: tents, beds and mattresses, emergency vehicles, 4x4 intervention cars, professional motor pumps, inflatable dam, emergency tools; 3) Joint strategy elaborated to guide 6 communities from the cross-border area and related organizations that are involved in emergency and risk situations management; 4) 4 Joint events that consisted of simulations and drills for around 40 people. The proposed simulations were based on a scenario and script of realistic events and participants were required to provide realistic responses based on existing procedures and resources; 5) 1 exchange of experience so that people involved in emergency services have a higher level of training 6) 1 Joint Strategy on risk and disaster management as a guide for communities in the cross-border area involved in emergency and risk management 7) Organisation of 5 joint activities in Hungary related to disaster and risk management, expecting an attendance of approximately 500 people. The main results: 1) The 3 emergency situations services are able to intervene more quickly and more effectively in disasters and incidents due to the improved infrastructure (equipment, vehicles, and tools for fire-fighting, flood management, extrication, intensive snow removal, and other types of environmental or man-made disasters), 2) A higher level of preparedness in case of approx. 100 people working on a contract basis or voluntarily at the involved emergency situations services, obtained as a result of participation in joint events organized in this field. 3) The enhanced community awareness and knowledge on disaster and risk management, and climate change adaptation. The main indicators: The Project Output indicator is 5/b 1 Population safeguarded by improved emergency response services. Through the project ROHU-48, 37,909 people are better protected by improved emergency response services. |