| 1st Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-54 |
| Project title | RiskMan Cooperating on risk prevention and disaster management in the Zerind- Újkígyós cross-border area |
| Priority axis | 5- Improve risk prevention and disaster management (Cooperation on risk-prevention and disaster management) |
| Investment priority | 5/b- Promoting investment to address specific risks, ensuring disaster resilience, and developing disaster management systems. |
| Implementation period | 25 Months (April 01, 2019 - April 30, 2021) |
| Objective | The project's main overall objective was to improve the quality of the existing system in addressing specific risks (prevention and management) and improving disaster resilience of the people from the Zerind - Újkígyós cross-border area in 22 months. |
| Partnership | Lead Beneficiary: Zerind Village ( Romania) |
|  | Project Partner: PP2: Újkígyós Town (Hungary) |
| TOTAL Budget | € 489,230.00 out of which ERDF € 415,845.50 Total eligible expenditure certified within the project: € 458,638.32 Budget execution: 93.75% |
| Summary | Through the ROHU-54 project, a new partnership for cross-border cooperation, between Zerind Village and Újkígyós Town, regarding risk management and prevention such as wildfires, fires, and storms, was created. The main activities implemented within the project: - Purchasing of specific equipment (2 trucks, 1 rapid response vehicle, 16 fire suits, 1 release equipment, 1 pump, 1 telescopic ladder, 1 chain saw, 1 generator, headphones, gloves, boots, etc.) and 1 screen interactive for video conferencing; - Organizing 4 joint simulation exercises (with 35 volunteers) - Organizing a certified vocational training course for two volunteers from Zerind, for a harmonized approach, and to improve the local services regarding the protection/assistance of the local population in case of emergency. - Organizing training for volunteer firefighters (20 participants) and one for advanced (5 participants) in Újkígyós - Organizing 4 joint workshops for better collaboration in the field of emergencies, with the involvement of 15 relevant participants from the Zerind -Újkígyós border area - Elaboration of a joint plan for the prevention and mitigation of risks for a unitary approach in emergencies, which addresses several 12 localities on both sides of the border. - Organizing 2 awareness campaigns for the local population, on prevention and reaction in emergencies, and on how intervention |

|  | teams manage emergencies. For this purpose, “Rescue Day” events were organized both in Zerind and in Újkígyós, each event attended by over 200 people (such activities: simulation of rescue exercises, educational activities, presentation of intervention teams and their activities to the local population). On April 30, 2021, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | The main deliverables of the project: 1) 4 Joint mock drills for approximately. 70 participants, 2 trainings out of which 1 is certified, for 27 participants from Zerind-Ujkigyos target area, to improve the knowledge of the local population regarding the prevention and intervention, reaction in case of emergencies; 2) A page on a social network was created for promoting the project and its activities - RISKMAN. 3) Purchase of equipment: 2 fire trucks, 1 rapid vehicle for Romanian partner and safety equipment for both partners. 4) 3 Joint workshops organised for min. 30 stakeholders and participants among local population representatives; 5) 1 Joint risk prevention and management plan; 6) activities of awareness raising for the local population - Rescue Day - for min. 400 people from the Zerind-Ujkigyos target area. Their knowledge about how to prevent and react in emergency situations, how emergency situations are handled by intervention teams, who are intervention team members etc. improved. The main results of the project: - 34,601 people better safeguarded by improved emergency services in Zerind -Újkígyós cross-border area, equipped with professional equipment procured within the project; - 1 Joint Plan for Emergency Situations and cooperation in case of disasters, including the methods and priority of use of the newly acquired equipment. - Increased awareness of the population from Zerind-Ujkigyos target area, in risk prevention management through the awareness-raising campaigns organized during the project implementation. The Programme Output Indicator: The Programme Output Indicator is “5/b 1 Population safeguarded by improved emergency response services”. Through the project ROHU-54, 34,601 persons are better protected as a result of its implementation. Social media: https://www.facebook.com/RiskMan-406267886887627/ Website/webpage:https://primariazerind.ro/category/romana/proiecte-cu-finantare- europeana/ |