| 2nd Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-161 |
| Project title | O-IKT-SETI O-IKT (Sport-Health-Tourism-Youth) |
| Priority axis | 6 – Promoting cross-border cooperation between institutions and citizens (Cooperation of institutions and communities) |
| Investment priority | 11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions (Cooperation for citizens) |
| Implementation period | 25 months (1st of December 2018 – 31st of December 2020) |
| Objective | The project’s main objective was to draw attention to a healthy, responsible, environmentally conscious lifestyle through orienteering sports. |
| Partnership | Lead Beneficiary: Regional Telecottages Public Association of South Hungarian Plain (Hungary) |
|  | Project partners: PP2: For Orienteering Foundation (Hungary) PP3: The Touristic Association Condor Club Arad (Romania) |
| TOTAL Budget | € 64,939.00, out of which ERDF € 55,198.15 Total eligible expenditure certified within the project: € 54,315.94 Budget execution: 83.64% |
| Summary | The project ROHU-161 aimed to intensify cooperation between cross-border communities, from Arad and Csongrád-Csanád counties, and promote a healthy lifestyle through sport. The main activities implemented within the project: - Organising activities to collect data (800 digitally recorded research documents such as interviews, pictures, and films), systematising and preparing them for selection and promotion on the portal; - Organising a seminar to select the areas where the events will be held and to select the values that will be promoted (40 values selected from 8 areas (5 RO+3 HU)); - Organising a 4-module online training/webinar to educate and inform the target group about the newly developed orienteering areas and to involve rural regions in digital development; - Developing a portal to promote the 8 selected areas and sports tourism in the border area; - Organising an orienteering map correction training for 14 people (7 from RO and 7 from HU); - Organising the map correction for 5 Romanian and 3 Hungarian regions selected, with teachers acting as proofreaders and mentors. 13 maps were produced in the 8 locations, with the involvement of students participating in the workshops. As a result, 38.58 square km of mapped areas were corrected; - Organising promotional orienteering events in 5 Romanian and 3 Hungarian settlements from the Programme area using the created maps and purchased devices, with 208 participants; - Purchasing equipment for carrying on the activities (such as 6 notebooks, 1 monitor, 2 mobile phones, 6 SD cards, 1 GPS, 1 Forestry laser rangefinder, 1 Kramer software, etc). On December 31, 2020, the project was successfully finalised. All activities provided in the project were completed (100%). The project drew attention to healthy lifestyles and the importance of outdoor activities and sports as key factors in improving quality of life for all age groups. |
| Main outcomes | Deliverables: - 1 bilingual portal developed to promote the natural and cultural values, the orienteering sports events, and the virtual routes from the 8 cross-border areas selected; - 8 map corrections for 5 selected Romanian areas (Căsoaia, Moneasa, Băile Felix, Sânnicolau de Munte, and Vârtop) and 3 Hungarian areas (Ásotthalom, Sándorfalva and Ópusztaszer Memorial Park) - 38,58 square km of mapped areas; - 8 orienteering sports tourism centres were established in the Programme areas (5 in Romania and 3 in Hungary - Căsoaia, Moneasa, Băile Felix, Sânnicolau de Munte, Vârtop, Sándorfalva, Ópusztaszer and Ásotthalom) through the 8 orienteering sports events organised for 208 participants; - 1 orienteering map correction training organised for 14 participants; - Webinar organized in 8 locations and online. Results: - Enhanced promotion of tourism, cultural heritage, and natural environments in the five Romanian and three Hungarian selected local areas. - Increased public awareness of healthy lifestyles, highlighting the importance of sports, agro-tourism, and ecotourism through the events organized within the project. Indicators: The Programme Output Indicator was „11/b2 Number of people directly involved in cross-border cooperation initiatives”. A total of 330 people from Romania and Hungary, directly involved in cross-border cooperation initiatives, participated in the ROHU–161 project activities. Website/webpage: https://o-sportturizmus.ertekek.hu/ Social media: Facebook O-IKT-SETI |