| 2nd Open Call -Normal Projects |  |
| --- | --- |
| Project code | ROHU-315 |
| Project title | COMSPORT ComSport-Together for the creation of an active social group |
| Priority axis | 6 - Promoting cross-border cooperation between institutions and citizens (Cooperation of institutions and communities) |
| Investment priority | 11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions |
| Implementation period | 15 months (1st of November 2018 – 31st of January 2020) |
| Objective | The main objective of the project was promoting cultural, artistic and sports activities by organising: sports competitions for children and adolescents (football, tennis, handball, karate), folk dance competitions and cooking competitions. |
| Partners | Lead Beneficiary: Commune Pusztaottlaka (Hungary) |
|  | Project Partner: PP2: UAT Curtici (Romania) |
| TOTAL Budget | € 80,000.00, out of which, ERDF € 68,000.00 Total eligible expenditure certified within the project: € 77,581.66 Budget execution: 96.98% |
| Summary | Project ROHU-315 improved the quality of life of local people and guests visiting the towns of Curtici (RO) and Pusztaottlaka (HU), by promoting a healthy lifestyle and sports practice. The main activities are: - Organizing 4 cross-border events, in Romania and Hungary, with cultural, artistic, and sport thematic sport contests between children's teams and adult teams (football, tennis, handball, karate); - Organizing folk-dance competitions; - Organizing culinary competitions; |

|  | - Acquisition of necessary equipment: outdoor furniture, tents, catering equipment, football team equipment, folkloric costumes etc.; - Rehabilitation of the sports bases in Curtici Town. On January 31, 2021, the project was successfully finalized. All activities provided in the project were completed (100%). |
| --- | --- |
| Main outcomes | Deliverables: - Four cross-border events were organized in Romania and Hungary, featuring cultural, artistic, and sports activities, including themed competitions between children’s teams and old-boys teams (football, tennis, handball, karate), as well as folk dance competitions and culinary contests. - Acquisition of the necessary equipment, including outdoor furniture, tents, catering equipment, football team equipment, folkloric costumes, etc. - Rehabilitation of the sports base in Curtici Town. Results: - Promotion of cultural, artistic, and sports life within local communities through the organization and development of common cross-border activities, including cultural, artistic, gastronomic, and sports events and competitions. - Conservation and transmission of moral, artistic, and sports values, supported through the organization of contests, festivals, and cultural manifestations. - Stimulation of creativity and talent among participants through involvement in artistic, cultural, and sports activities. - The organization of gastronomic activities and sports competitions contributed to increased community engagement and participation. Indicators: The Programme Output Indicator was „11/b2 Number of people participating in cross-border cooperation initiatives”. Project ROHU–315 contributed by reaching a number of 1,100 participants, which took part in the events of the project. |