
	2nd Open Call- Normal Projects

	Project code
	ROHU-162

	Project title
	GEOCLUSTERBHB
Cluster for Geography, Heritage and Sustainable Development in Bihor
- Hajdu Bihar Crossborder Area

	Priority axis
	6 – Promoting cross-border cooperation between institutions and citizen (Cooperation of institutions and communities)

	Investment priority
	11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions (ETC-CB).

	Implementation period
	23 months (1st of December 2018 – 31st of October 2020)

	

Objective
	The main objective of the project was to create a working base that will be used by the public administration which will contribute to the improvement of the teaching and learning process in schools within the cross-border region.

	


Partnership
	Lead Beneficiary:
University of Oradea (Romania)

	
	Project Partners:
PP2: Bihor Destination Management Agency (Romania) PP3: Érmelléki Folk-High School (Hungary)

	TOTAL Budget
	€ 216,266.70, out of which, ERDF € 183,826.69
Total eligible expenditure certified within the project: € 199,226.02
Budget execution: 92.12%

	


Summary
	The project ROHU-162 aimed to emphasize the role of geography and territorial planning within the rural, urban or architectural landscape of the Bihor-Hajdú-Bihar region, within the social and economic fields, through the organization and development of a series of Romanian- Hungarian joint thematic actions.

The main activities implemented within the project:
· Organizing 9 workshops with the participation of various people: representatives of local public administration, private sector, NGOs, youth associations, students, and teachers, from Bihor and Hajdú-Bihar counties, in order to interconnect the real practitioners' market with the educational area:
· Updating and improving the knowledge of physical and human Geography;
· Destination Management. Models and good practices
· Use of digital geographic data and free GIS software
· Problems of environmental geography 
· Knowledge and promotion of natural heritage
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	· Unconventional energy and sustainable development
· Techniques of communication
· Modern techniques and methods of teaching / learning Geography in schools
· Organizing a round table: Presenting the elaborated support materials
· Creating a specific package that contains materials regarding the elaboration of the local Bihor - Hajdú Bihar geographical horizon:
· 500 Atlases of Bihor County Local Geographic Horizon,
· 500 Heritage Albums of the Hajdu-Bihar County
· 1000 brochure: Educational and Recreational Cross- Border Trails
· Creating 1 Integrated System that contains a web portal and a mobile phone application
· Creating a short documentary film about natural and cultural heritage in the cross-border area;
· Organizing 2 field trips and 4 specialized visits, with the participation of two schools from Bihor County and two from Hajdu Bihar County, in order to successfully transfer the know-how between local governments and education institutions in the field of geography, territorial planning, environment and education.

On October 31, 2020, the project was successfully finalized. 
All activities provided in the project were completed (100%).

	Main outcomes
	The main deliverables of the project are:
1) 1 Workshop on Destination Management - Models and good practices;
2) 1 Workshop on Use of digital geographic data and free GIS software;
3) 1 Workshop on Problems of environmental geography;
4) 1 Workshop on Modern techniques and methods of teaching / learning Geography in schools;
5) 1 Atlas of Bihor County Local Geographic Horizon;
6) 1 Heritage Album of the Hajdu-Bihar County;
7) 1 Integrated System - GIS and WEB Portal and mobile phone application were developed. Databases is available in ESRI, where information about targets, routes, and categories are stored. the mobile application is used for browsing and receiving messages (goal and event notifications) from IT administrators.
8) 1 Short Documentary Film about heritage in crossborder area.

The main results of the project are:
1)  Modern technological tools and techniques in teaching and applying geographical data created.
2) Resources on local heritage in the cross-border area created (a local Atlas and a Heritage Album published, a documentary produced), to be   used in schools in Hajdu-Bihar and Bihor Counties in order to increase the knowledge of local specificities.
3) This project aimed to outline the role of geography and territorial planning within the rural, urban or architectural landscape and within the social and economic fields of our society.

The main output indicator:
The Programme Output Indicator is „11/b1 Number of institutions directly involved in cross border cooperation initiatives”. Through the project ROHU–162, 3 institutions were directly involved in cross-border cooperation initiatives.
The collaboration of the three partners within this project consolidated the cross-border links between the educational institutions at different levels: university, gymnasium and lyceum, also at local governments, by valorizing the potential of the cross-border area regarding natural and cultural heritage.

Website/webpage: 
https://explorebihor.ro/ 
https://www.amdbihor.ro/rohu-162/ 
https://rohu162.eu/
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