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	2nd Open Call – Normal Projects

	Project code
	ROHU-202

	Project title
	seruMaros
Mures/Maros that binds us

	Priority axis
	6 – Promoting cross-border cooperation between institutions and citizens (Cooperation of institutions and communities)

	Investment priority
	11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions

	Implementation period
	27 months (August 1, 2018 – October 31, 2021), out of which 3 months of suspension

	Objective
	The main objective of the project was to establish a cross-border framework to facilitate community cohesion and provide opportunities for cooperation, mainly for the population of the localities from the Mureș/Maros River shores.

	Partnership
	Lead Beneficiary: Diaspora Foundation (Romania)

	
	Project Partner: Southern Great Plain Regional Research Society for Social Sciences (Hungary)

	TOTAL Budget
	€ 60,495.00, out of which, ERDF € 51,420.75
Total eligible expenditure certified within the project: € 59,356.28
Budget execution: 98.11%

	Summary
	The project ROHU-202 aimed at creating a framework of cross-border collaboration between the 8 communities situated on both shores of the Mureș River: Igriș, Cenad, Pecica, Semlac (RO), and Deszk, Magyarcsanád, Maroslele, Ferencszállás (HU), by involving young people and adults from these communities in working together and achieving joint goals.

The main activities implemented within the project: 
· Establishing local clubs of young people in the 8 Romanian and Hungarian localities: Igriș, Cenad, Pecica, Semlac, Deszk, Magyarcsanád, Maroslele, Ferencszállás;
· Organizing joint cultural events: a workshop for club leaders, 2 picnics with the involvement of target groups of both sides of the border, and preparing a thematic bilingual workbook about Mureș; 
· Preparing a film, in the form of a virtual exposition, in which each of the 8 localities involved had the opportunity to present their activities and works.

On October 31st, 2021, the project was successfully finalized.
All activities provided in the project were completed (100%).

	Main outcomes
	Deliverables:
1. Eight local clubs for children were established- four in Romania (Cenad, Pecica, Igris, Semlac) and four in Hungary (Deszk, Magyarcsanád, Maroslele, Ferencszállás)- to engage in workshop activities such as painting, crafting, photo collage, poetry, and film. 
2. Joint cultural events were organized, including a workshop for club leaders and two picnics for target groups from both sides of the border; a thematic bilingual workbook about the Mureș/Maros River was also developed. 
3. A film was produced as a virtual exhibition, in which each of the eight localities presented their activities and created works.
Results:
1. Established cross-border framework that supports community cohesion and provides cooperation opportunities, particularly for residents of localities along the Mureș/Maros River. 
2. Increased opportunities for cross-border partnerships, leading to improved cooperation between the communities.
Indicators:
Programme Output Indicator was „11/b2 Number of people participating in cross-border cooperation initiatives”. Project ROHU–202 contributed to this indicator by reaching 134 people from the two communities situated on the shores of the Mureș River, as participants in the events organized.
Website/webpage:
· http://www.maros-mures.eu
· https://www.diasporatm.ro/ro/proiectul-serumaros/
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