
	   2nd Open Call- Normal Projects

	Project code
	ROHU-265
	

	Project title
	TOGETHER
LET'S CELEBRATE OUR TRADITIONS TOGETHER
	

	Priority axis
	6 – Promoting cross-border cooperation between institutions and citizen (Cooperation of institutions and communities)
	

	Investment priority
	11/b - Promoting legal and administrative cooperation and cooperation between citizens and institutions (ETC-CB)
	

	Implementation period
	18 months (1st of November2018 – 30th of April 2020)
	

	
Objective
	The project's main objective was to increase the development of long- term sustainable communities in Cetariu (RO) and Kaba (HU) by using cross-border patrimony as a local resource and asset.
	

	

Partnership
	Lead Beneficiary:
Cetariu Commune (Romania)
	

	
	Project Partner:
PP2: Kaba City Local Government (Hungary)
	

	TOTAL Budget
	€ 70,400.00 out of which ERDF € 59,840.00
Total eligible expenditure certified within the project: € 69,417.75
Budget execution: 98.60%
	

	




Summary
	The project ROHU-265 organized a series of multi-annual events to promote cultural diversity and local traditions.

The main activities implemented within the project:
· organizing two cultural events in Cetariu (RO), through which will be presented folk ensembles and sports competitions for young people;
· organizing three cultural events in Kaba (HU), which have a rich
heritage value; 
· acquisition by the Lead Beneficiary of specific pieces of equipment used for organizing cultural events: mobile scene and sound system, 
· acquisition by Project Partner 2 of a specific illumination system, which will be used for winter events.

On April 30, 2020, the project was successfully finalized. All activities provided in the project were completed (100%).
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Main outcomes
	The project’s main deliverables are:
1) 13 pieces of equipment: 1 mobile scene, 2 specific electric systems: 1 sound and 1 illumination system, 10 sets of tables and wooden benches necessary for the events organized within the project;
2) 5 annual events organized in Cetariu and Kaba, 2 in Cetariu and 3 in Kaba. Folk groups and artists from both sides participated in events in Cetariu, and also sports competitions between teams from both communes were organized. The annual events organized in Cetariu were held in summer (youth & children) and in autumn of 2019 (Grapes Festival), while the events in Kaba were related to the New Bread Feast and Advent celebration in 2019 and Carnival in February 2020.

The project’s main results are:
1) Adequate equipping of the 2 communes with the necessary endowments, to be able to organize annual events for the local communities.
2) Increased promotion of the cooperation between citizens, to bring communities closer and strengthen the relationship between them. The citizens of the two countries will be more aware of the specific traditions and will interact actively in an informal frame, such as concerts and cooking contests. 

The main output indicator:
The Programme Output Indicator is „11/b2 Number of people participating in cross-border cooperation initiatives”. Through project ROHU – 265, 825 people participated in the project’s cultural events.

The partners' collaboration in this project raised citizens’ awareness of the specific traditions of both localities and created a framework in which people can gather and exchange their cultural values.
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