| 2nd Open Call- Normal Projects |  |
| --- | --- |
| Project code | ROHU-283 |
| Project title | CCC_MB Sustainable cross-border cooperation for citizens between Marghita and Berettyóújfalu municipalities |
| Priority axis | 6 - Promoting cross-border cooperation between institutions and citizens (Cooperation of institutions and communities) |
| Investment priority | 11/b2 - Promoting legal and administrative cooperation and cooperation between citizens and institutions. Cooperation for citizens |
| Implementation period | 24 months (December 1, 2018 – November 30, 2020) |
| Objective | The project's main objective was the sustainable cooperation between the institutions and communities from Marghita and Berettyóújfalu. |
| Partnership | Lead Beneficiary: Marghita Municipality (Romania) |
|  | Project Partners: PP2: Berettyó Cultural Center (Hungary) |
| Total Budget | € 80,000.00, out of which ERDF € 68,000.00 Total eligible expenditure certified within the project: € 79,418.30 Budget execution: 98.02% |
| Summary | The project ROHU-128 aimed to intensify the cooperation between institutions and communities from Marghita and Berettyóújfalu. The main activities implemented within the project: - developing a Collaboration Protocol for promoting cultural diversity and traditions between the two partners and the local civil society involved in cultural events - organizing 2 joint cross-border cultural events in Marghita - organizing 2 joint cross-border cultural events in Berettyóújfalu - purchasing stage equipment for both partners On November 30, 2020, the project was successfully finalized. All activities provided in the project were completed (100%). |

| Main outcomes | Deliverables: - Eight active NGOs (4 from Romania and 4 from Hungary) were brought together to identify cultural needs and jointly plan local and cross-border cultural activities between Marghita and Berettyóújfalu. - Four joint cross-border cultural events were organized in Marghita and Berettyóújfalu, aimed at preserving and promoting cultural diversity and traditions. - Two technical equipment items were purchased, namely a stage cover and a concert stage. Results: - Increased engagement of civil society from Marghita and Berettyóújfalu in joint cultural activities, bringing institutions and citizens closer together, fostering network creation, and strengthening existing cross-border cooperation. - Promotion and preservation of cultural diversity and traditions, contributing to the safeguarding and promotion of shared cultural heritage. - Improved sustainability of cross-border events, ensured by the purchased equipment, enabling increased participation and supporting long-term citizen cooperation initiatives. Indicators: The Programme Output Indicator was: “11/b2 Number of people participating in cross-border cooperation initiatives”. Through this project 6,120 people participated in cross-border cultural events. |
| --- | --- |