
	2nd Open Call- Normal Projects

	Project code
	ROHU-283

	Project title
	CCC_MB 
Sustainable cross-border cooperation for citizens between Marghita and Berettyóújfalu municipalities

	Priority axis
	6 - Promoting cross-border cooperation between institutions and citizens (Cooperation of institutions and communities)

	Investment priority
	11/b2	-	Promoting	legal	and	administrative	cooperation	and cooperation between citizens and institutions. Cooperation for citizens

	Implementation period
	24 months (December 1, 2018 – November 30, 2020)

	Objective
	The project's main objective was the sustainable cooperation between the institutions and communities from Marghita and Berettyóújfalu.

	

Partnership
	Lead Beneficiary:
Marghita Municipality (Romania)

	
	Project Partners:
PP2: Berettyó Cultural Center (Hungary)

	Total Budget
	€ 80,000.00, out of which ERDF € 68,000.00

Total eligible expenditure certified within the project: € 79,418.30

Budget execution: 98.02%

	





Summary
	The project ROHU-128 aimed to intensify the cooperation between institutions and communities from Marghita and Berettyóújfalu.

The main activities implemented within the project:
· developing a Collaboration Protocol for promoting cultural diversity and traditions between the two partners and the local civil society involved in cultural events
· organizing 2 joint cross-border cultural events in Marghita
· organizing 2 joint cross-border cultural events in Berettyóújfalu
· purchasing stage equipment for both partners

On November 30, 2020, the project was successfully finalized. All activities provided in the project were completed (100%).
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Main outcomes
	Deliverables:
1. Eight active NGOs (4 from Romania and 4 from Hungary) were brought together to identify cultural needs and jointly plan local and cross-border cultural activities between Marghita and Berettyóújfalu. 
2. Four joint cross-border cultural events were organized in Marghita and Berettyóújfalu, aimed at preserving and promoting cultural diversity and traditions. 
3. Two technical equipment items were purchased, namely a stage cover and a concert stage.

Results:
1. Increased engagement of civil society from Marghita and Berettyóújfalu in joint cultural activities, bringing institutions and citizens closer together, fostering network creation, and strengthening existing cross-border cooperation. 
2. Promotion and preservation of cultural diversity and traditions, contributing to the safeguarding and promotion of shared cultural heritage. 
3. Improved sustainability of cross-border events, ensured by the purchased equipment, enabling increased participation and supporting long-term citizen cooperation initiatives.

Indicators:
The Programme Output Indicator was: “11/b2 Number of people participating in cross-border cooperation initiatives”. Through this project
6,120 people participated in cross-border cultural events.
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