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	Project code
	ROHU-449 FAF

	
Project Title
	IPHEALTH - FA Phase
Integrated project for sustainable development in the mountain area of Bihor County, improvement of access and development in health care services in case of medical interventions for emergency situations - FA Phase

	Priority Axis
	4 – Improving health care services (Cooperating on health care and prevention)

	

Investment priority
	9/a – Investment in health and social infrastructure which contributes to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services.

	Implementation
period
	86 months (August 01, 2019 – September 30, 2026)
The project is included in the non-functional category.

	




Partnership
	LB:  Bihor County Council (Romania)
PP2: Local Government of Berettyóújfalu City (Hungary) PP3: Municipality of Oradea (Romania)
PP4: Municipality of Marghita (Romania) PP5: Municipality of Salonta (Romania) PP6: Town of Aleșd (Romania)
PP7: Municipality of Beiuș (Romania)
PP8: University of Oradea, Faculty of Medicine and Pharmacy (Romania)
AP1 (LP Associated Partner): Mountain and Cave Rescue Service of Bihor County
/ Mountain Rescue Association of Bihor County (Romania)
AP2 (PP2 Associated Partner): Gróf Tisza István Hospital (Hungary)

	



Project budget
	Total 13,049,572.49 EUR, out of which EDRF 10,706,344.21 EUR
LB: 1,442,829.94 EUR ERDF, 220,629.44 EUR national co-financing PP2: 801,927.26 EUR ERDF, 94,339.17 EUR national co-financing PP3: 6,194,147 EUR ERDF, 947,267.29 EUR national co-financing PP4: 228,072.00 EUR ERDF, 34,878.92 EUR national co-financing
PP5: 230,917.80 EUR EUR ERDF, 35,314.13 EUR national co-financing PP6: 228,072.00 EUR ERDF, 34,878.92 EUR national co-financing PP7: 232,279.60 EUR ERDF, 35,515.93 EUR national co-financing
PP8: 1,348,098.43 EUR ERDF, 206,167.48 EUR national co-financing

	
Objective
	The improvement of oncology, the improvement of emergency medical services by an integrated system, the establishment of unified telemedicine infrastructure, the establishment of unified e-health, telecare system, training and tuition of medical professionals.

	Summary
	Project’s main activities:
· LB: building and equipping two emergency medical centres in the mountain area, Padiș and Stâna de Vale, that will be operated by AP1;
· PP2: reconstructing a building of the local hospital (Gróf Tisza István Hospital-AP2) and establishing a modern physical medicine and rehabilitation centre that will be operated by the medical professionals of the local hospital;
· PP3: establishing an open telemedicine system and equipping the County and Municipal hospitals from Oradea with modern digital radiography devices, Angio CT, Spect CT for oncological and endocrine diagnosis;
· PP4, PP5, PP6, PP7: equipping the local hospitals with modern digital radiography and echography devices and interconnecting the hospitals to the ones in Oradea;
· PP8: reconstructing one of its buildings and establishing a learning and research centre, a Learning Centre for Continuing Medical Education.

The partners also contributed to the establishment of a unified system that connects and stores the patients’ information from all emergency clinics in an organised database, accessible for all medical professionals, and of a telemedicine network, and organised 2 cross-border trainings for Romanian and Hungarian medical professionals in the newly constructed and equipped medical training centre.

Website/webpage: https://iphealth.ro/

	Main outcomes
	Deliverables
1) Two first aid points in the mountain area of Bihor County were established and equipped, in Padis and Stana de Vale; the purchase of modern searching and rescue vehicles and equipment, as well as first aid equipment, was completed.
2) Medical equipment used in physical medicine and rehabilitation was purchased and installed in Berettyóújfalu border area: treatment beds, doctor’s chairs, low frequency electrotherapy devices, laser showers, combined electrotherapy devices, vacuum therapy devices, ultrasound therapy devices, extension device, laser therapy device, interior exercise equipment: stationary bike, treadmill, wall bars, different devices and equipment used in balneotherapy: galvanic bath, carbonic acid bath, saturator, other tools for weight bath, massage bath,  EKG, defibrillator, ergotherapy devices and tools and other necessary items for the staff for the well-functioning of the physical medicine and rehabilitation department of the hospital;
3) Emergency and first aid vehicles and equipment were purchased and installed in Bihor County: specialised ambulances for medical intervention, including one for patients at critical health risks were added to the Bihor Couty Hospital fleet. 1 state-of-the-art angio CT was installed in Bihor County Hospital, as well as 1 SPECT CT. Video laryngoscopes with LCD screen and data storage, digital radiology devices, CT devices, and hospital beds for patients in intensive care units were also achieved.
4) SA telemedicine system with one datacentre and telemedicine kits used for collecting patient data was established in Bihor County: all county, municipal and town hospitals were connected to County Clinical Emergency Hospital of Oradea, thus the medical professionals from the County Emergency Hospital are now able to perform online consultations and diagnosis, as well as to receive and consult digital images obtained through the echography unites, in real time;
5) A cross-border medical training centre was established within the University of Oradea by reconstructing an existing building and expanding it in order to provide the necessary space for the medical training. Apart from the construction, the partner also purchased all the necessary equipment for the learning process in eight different modules: anatomy, general medicine, surgery, echography, pharmacy, dental medicine, emergency medicine, and endoscopy.

Results
1) Localisation of injured patients and the intervention of medical professionals in a shortened period of time is ensured through the use of the specialised search and rescue equipment purchased within the project.
2) The quality of the emergency health care services in Oradea and its surroundings is improved through the modern emergency screening equipment already purchased and put into operation through the project.
4) A larger population has better access to health care services; thus better mental and physical health of the target cross-border population is ensured.
6) Medical trainings were provided for medical specialists in the area addressed by the project, in the majority of medical disciplines, focusing, however, on emergency medicine and oncology, with the help of the medical simulators already purchased within the project. The emergency health care and rescue services provided to the population have, as a result, a better quality.

The Programme Output Indicator are „9/a 1 Population having access to improved health services” and „9/a 2 Number of health-care departments affected by modernized equipment”. 
Through project ROHU–449, a number of 700.000 persons benefitted from improved health care services and a number of 9 health-care units were built/renovated/modernized and endowed with new equipment.
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Concept Note
	Project code: ROHU-275
Implementation period: October 01, 2018 – March 31, 2019
Total budget 77,197.40 EUR, out of which ERDF 65,617.79 EUR. Preparation activities for developing the Full Application Form.



image1.png
11ILCIICTYy

Romania-Hungary

European Regional Development Fund




image2.png




image3.png




image4.png




image5.png




